## All_Tasks
Scope | NETA_Standard | Task_ID | Task | Apparatus | Designation | Drawing | Date Due | Notes | Assessment | DATASHEET | DATE COMPLETED | NOTES2 | % COMPLETION | TASK DELAYS | Apparatus Hours | Remaining Hours | ACTUAL HOURS | STATUS | AVAILABILITY | PRIORITY | Apparatus Category
Emergency Generator Dist | ATS | 1.1.1 | 2.0MW Gen Distribution | Switchboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Switchboard
Emergency Generator Dist | ATS | 1.1.2 | 2.0MW Gen Distribution | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE |  |  | 0 |  | 3 | 3 | 3 |  |  |  | Circuit Breaker - Primary
Emergency Generator Dist | ATS | 1.1.3 | 2.0MW Gen Distribution | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE |  |  | 0 |  | 3 | 3 | 3 |  |  |  | Circuit Breaker - Primary
Emergency Generator Dist | ATS | 1.1.4 | 2.0MW Gen Distribution | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE |  |  | 0 |  | 3 | 3 | 3 |  |  |  | Circuit Breaker - Primary
Emergency Generator Dist | ATS | 1.2.1 | Electrode Room | Automatic Transfer Switch - (IR/DLRO) | [5 empty] | FALSE | 45896 |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | ATS
Emergency Generator Dist | ATS | 1.2.2 | Electrode Room | Automatic Transfer Switch - (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | ATS
Emergency Generator Dist | ATS | 1.2.3 | Electrode Room | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
Emergency Generator Dist | ATS | 1.2.4 | Electrode Room | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.2.5 | Electrode Room | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.2.6 | Electrode Room | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.2.7 | Electrode Room | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.2.8 | Electrode Room | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.2.9 | Electrode Room | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.2.10 | Electrode Room | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.2.11 | Electrode Room | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.2.12 | Electrode Room | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Emergency Generator Dist | ATS | 1.2.13 | Electrode Room | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Emergency Generator Dist | ATS | 1.2.14 | Electrode Room | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Emergency Generator Dist | ATS | 1.2.15 | Electrode Room | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
Emergency Generator Dist | ATS | 1.2.16 | Electrode Room | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
Emergency Generator Dist | ATS | 1.2.17 | Electrode Room | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
Emergency Generator Dist | ATS | 1.3.1 | 1.5MW Gen Distribution | Switchboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Switchboard
Emergency Generator Dist | ATS | 1.3.2 | 1.5MW Gen Distribution | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE |  |  | 0 |  | 3 | 3 | 3 |  |  |  | Circuit Breaker - Primary
Emergency Generator Dist | ATS | 1.3.3 | 1.5MW Gen Distribution | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE |  |  | 0 |  | 3 | 3 | 3 |  |  |  | Circuit Breaker - Primary
Emergency Generator Dist | ATS | 1.3.4 | 1.5MW Gen Distribution | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE |  |  | 0 |  | 3 | 3 | 3 |  |  |  | Circuit Breaker - Primary
Emergency Generator Dist | ATS | 1.4.1 | A1 & A2 Emerg Distribution | Automatic Transfer Switch - (IR/DLRO) | [5 empty] | FALSE | 45896 |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | ATS
Emergency Generator Dist | ATS | 1.4.2 | A1 & A2 Emerg Distribution | Automatic Transfer Switch - (IR/DLRO) | [5 empty] | FALSE | 45896 |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | ATS
Emergency Generator Dist | ATS | 1.4.3 | A1 & A2 Emerg Distribution | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
Emergency Generator Dist | ATS | 1.4.4 | A1 & A2 Emerg Distribution | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.4.5 | A1 & A2 Emerg Distribution | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.4.6 | A1 & A2 Emerg Distribution | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.4.7 | A1 & A2 Emerg Distribution | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.4.8 | A1 & A2 Emerg Distribution | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.4.9 | A1 & A2 Emerg Distribution | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.4.10 | A1 & A2 Emerg Distribution | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.4.11 | A1 & A2 Emerg Distribution | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.4.12 | A1 & A2 Emerg Distribution | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.4.13 | A1 & A2 Emerg Distribution | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.4.14 | A1 & A2 Emerg Distribution | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Emergency Generator Dist | ATS | 1.4.15 | A1 & A2 Emerg Distribution | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Emergency Generator Dist | ATS | 1.4.16 | A1 & A2 Emerg Distribution | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
Emergency Generator Dist | ATS | 1.5.1 | A1 & A2 Emerg Distribution | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
Emergency Generator Dist | ATS | 1.5.2 | A1 & A2 Emerg Distribution | Automatic Transfer Switch - (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | ATS
Emergency Generator Dist | ATS | 1.5.3 | A1 & A2 Emerg Distribution | Automatic Transfer Switch - (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | ATS
Emergency Generator Dist | ATS | 1.5.4 | A1 & A2 Emerg Distribution | Automatic Transfer Switch - (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | ATS
Emergency Generator Dist | ATS | 1.5.5 | A1 & A2 Emerg Distribution | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.5.6 | A1 & A2 Emerg Distribution | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.5.7 | A1 & A2 Emerg Distribution | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.5.8 | A1 & A2 Emerg Distribution | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.5.9 | A1 & A2 Emerg Distribution | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.5.10 | A1 & A2 Emerg Distribution | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.5.11 | A1 & A2 Emerg Distribution | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.5.12 | A1 & A2 Emerg Distribution | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Emergency Generator Dist | ATS | 1.5.13 | A1 & A2 Emerg Distribution | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Emergency Generator Dist | ATS | 1.5.14 | A1 & A2 Emerg Distribution | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Emergency Generator Dist | ATS | 1.5.15 | A1 & A2 Emerg Distribution | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.1.1 | SLD 1FO-E653 | Automatic Transfer Switch - (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | ATS
Datacenter Distribution | ATS | 2.1.2 | SLD 1FO-E653 | Automatic Transfer Switch - (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | ATS
Datacenter Distribution | ATS | 2.1.3 | SLD 1FO-E653 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
Datacenter Distribution | ATS | 2.1.4 | SLD 1FO-E653 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
Datacenter Distribution | ATS | 2.1.5 | SLD 1FO-E653 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
Datacenter Distribution | ATS | 2.1.6 | SLD 1FO-E653 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
Datacenter Distribution | ATS | 2.1.7 | SLD 1FO-E653 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE |  |  | 0 |  | 3 | 3 | 3 |  |  |  | Circuit Breaker - Primary
Datacenter Distribution | ATS | 2.1.8 | SLD 1FO-E653 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE |  |  | 0 |  | 3 | 3 | 3 |  |  |  | Circuit Breaker - Primary
Datacenter Distribution | ATS | 2.1.9 | SLD 1FO-E653 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE |  |  | 0 |  | 3 | 3 | 3 |  |  |  | Circuit Breaker - Primary
Datacenter Distribution | ATS | 2.1.10 | SLD 1FO-E653 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE |  |  | 0 |  | 3 | 3 | 3 |  |  |  | Circuit Breaker - Primary
Datacenter Distribution | ATS | 2.1.11 | SLD 1FO-E653 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE |  |  | 0 |  | 3 | 3 | 3 |  |  |  | Circuit Breaker - Primary
Datacenter Distribution | ATS | 2.1.12 | SLD 1FO-E653 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE |  |  | 0 |  | 3 | 3 | 3 |  |  |  | Circuit Breaker - Primary
Datacenter Distribution | ATS | 2.1.13 | SLD 1FO-E653 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE |  |  | 0 |  | 3 | 3 | 3 |  |  |  | Circuit Breaker - Primary
Datacenter Distribution | ATS | 2.1.14 | SLD 1FO-E653 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE |  |  | 0 |  | 3 | 3 | 3 |  |  |  | Circuit Breaker - Primary
Datacenter Distribution | ATS | 2.1.15 | SLD 1FO-E653 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
Datacenter Distribution | ATS | 2.2.1 | SLD 1FO-E654 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
Datacenter Distribution | ATS | 2.2.2 | SLD 1FO-E654 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
Datacenter Distribution | ATS | 2.2.3 | SLD 1FO-E654 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE |  |  | 0 |  | 3 | 3 | 3 |  |  |  | Circuit Breaker - Primary
Datacenter Distribution | ATS | 2.2.4 | SLD 1FO-E654 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE |  |  | 0 |  | 3 | 3 | 3 |  |  |  | Circuit Breaker - Primary
Datacenter Distribution | ATS | 2.2.5 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.6 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.7 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.8 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.9 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.10 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.11 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.12 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.13 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.14 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.15 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.16 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.17 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.18 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.19 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.20 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.21 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.22 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.23 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.24 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.25 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.26 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.27 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.28 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.29 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.30 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.31 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
Datacenter Distribution | ATS | 2.2.32 | SLD 1FO-E654 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.1 | 1F0AS-SS-A-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45880 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.1.2 | 1F0AS-SS-A-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45880 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.1.3 | 1F0AS-SS-A-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45876 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.1.4 | 1F0AS-SS-A-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45880 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.1.5 | 1F0AS-SS-A-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45880 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.1.6 | 1F0AS-SS-A-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45880 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.1.7 | 1F0AS-SS-A-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45880 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.1.8 | 1F0AS-SS-A-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A1 Electrical Room | ATS | 3.1.9 | 1F0AS-SS-A-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A1 Electrical Room | ATS | 3.1.10 | 1F0AS-SS-A-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 | 2 | 4 | 4 | 6 |  |  |  | Distribution Board
A1 Electrical Room | ATS | 3.1.11 | 1F0AS-SS-A-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 | NOT STARTED |  |  | Panelboard
A1 Electrical Room | ATS | 3.1.12 | 1F0AS-SS-A-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.1.13 | 1F0AS-SS-A-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.1.14 | 1F0AS-SS-A-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.1.15 | 1F0AS-SS-A-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.1.16 | 1F0AS-SS-A-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.1.17 | 1F0AS-SS-A-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.18 | 1F0AS-SS-A-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.19 | 1F0AS-SS-A-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.20 | 1F0AS-SS-A-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.21 | 1F0AS-SS-A-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.22 | 1F0AS-SS-A-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.23 | 1F0AS-SS-A-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.24 | 1F0AS-SS-A-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.25 | 1F0AS-SS-A-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.26 | 1F0AS-SS-A-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.27 | 1F0AS-SS-A-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.28 | 1F0AS-SS-A-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.29 | 1F0AS-SS-A-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.30 | 1F0AS-SS-A-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.31 | 1F0AS-SS-A-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.32 | 1F0AS-SS-A-01 | Bus Duct - Low Voltage (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Bus Duct
A1 Electrical Room | ATS | 3.1.33 | 1F0AS-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.34 | 1F0AS-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.35 | 1F0AS-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.36 | 1F0AS-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.37 | 1F0AS-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.38 | 1F0AS-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.39 | 1F0AS-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.40 | 1F0AS-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.1.41 | 1F0AS-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.2.1 | 1F0AS-SS-A-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45877 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.2.2 | 1F0AS-SS-A-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45877 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.2.3 | 1F0AS-SS-A-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45876 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.2.4 | 1F0AS-SS-A-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45876 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.2.5 | 1F0AS-SS-A-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45876 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.2.6 | 1F0AS-SS-A-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45876 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.2.7 | 1F0AS-SS-A-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45876 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.2.8 | 1F0AS-SS-A-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45877 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.2.9 | 1F0AS-SS-A-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45880 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.2.10 | 1F0AS-SS-A-02 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A1 Electrical Room | ATS | 3.2.11 | 1F0AS-SS-A-02 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A1 Electrical Room | ATS | 3.2.12 | 1F0AS-SS-A-02 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A1 Electrical Room | ATS | 3.2.13 | 1F0AS-SS-A-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.2.14 | 1F0AS-SS-A-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.2.15 | 1F0AS-SS-A-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.2.16 | 1F0AS-SS-A-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.2.17 | 1F0AS-SS-A-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.2.18 | 1F0AS-SS-A-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.2.19 | 1F0AS-SS-A-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.2.20 | 1F0AS-SS-A-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.2.21 | 1F0AS-SS-A-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.2.22 | 1F0AS-SS-A-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.2.23 | 1F0AS-SS-A-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.2.24 | 1F0AS-SS-A-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.2.25 | 1F0AS-SS-A-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.2.26 | 1F0AS-SS-A-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.2.27 | 1F0AS-SS-A-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.2.28 | 1F0AS-SS-A-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.3.1 | 1F0AS-SS-B-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45877 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.3.2 | 1F0AS-SS-B-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45877 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.3.3 | 1F0AS-SS-B-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45877 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.3.4 | 1F0AS-SS-B-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45880 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.3.5 | 1F0AS-SS-B-01 | Bus Duct - Low Voltage (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Bus Duct
A1 Electrical Room | ATS | 3.4.1 | 1F0AS-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45877 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.4.2 | 1F0AS-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45876 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.4.3 | 1F0AS-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45877 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.4.4 | 1F0AS-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45880 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.4.5 | 1F0AS-SS-B-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.4.6 | 1F0AS-SS-B-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.4.7 | 1F0AS-SS-B-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.4.8 | 1F0AS-SS-B-02 | Bus Duct - Low Voltage (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Bus Duct
A1 Electrical Room | ATS | 3.4.9 | 1F0AS-SS-B-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.4.10 | 1F0AS-SS-B-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.4.11 | 1F0AS-SS-B-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.4.12 | 1F0AS-SS-B-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.4.13 | 1F0AS-SS-B-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.1 | 1F0AS-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45877 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.5.2 | 1F0AS-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45880 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.5.3 | 1F0AS-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45876 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.5.4 | 1F0AS-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE |  |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.5.5 | 1F0AS-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.5.6 | 1F0AS-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.5.7 | 1F0AS-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.5.8 | 1F0AS-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.5.9 | 1F0AS-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.5.10 | 1F0AS-SS-B-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.11 | 1F0AS-SS-B-03 | Bus Duct - Low Voltage (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Bus Duct
A1 Electrical Room | ATS | 3.5.12 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.13 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.14 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.15 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.16 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.17 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.18 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.19 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.20 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.21 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.22 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.23 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.24 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.25 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.26 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.27 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.28 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.29 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.30 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.31 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.32 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.33 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.5.34 | 1F0AS-SS-B-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.6.1 | 1F0AS-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45880 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.6.2 | 1F0AS-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45875 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.6.3 | 1F0AS-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45876 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.6.4 | 1F0AS-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45877 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.6.5 | 1F0AS-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45875 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.6.6 | 1F0AS-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45880 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.6.7 | 1F0AS-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45875 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.6.8 | 1F0AS-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45876 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.6.9 | 1F0AS-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45880 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.6.10 | 1F0AS-SS-B-04 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A1 Electrical Room | ATS | 3.6.11 | 1F0AS-SS-B-04 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A1 Electrical Room | ATS | 3.6.12 | 1F0AS-SS-B-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.6.13 | 1F0AS-SS-B-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.6.14 | 1F0AS-SS-B-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.6.15 | 1F0AS-SS-B-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.6.16 | 1F0AS-SS-B-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.6.17 | 1F0AS-SS-B-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.6.18 | 1F0AS-SS-B-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.6.19 | 1F0AS-SS-B-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.6.20 | 1F0AS-SS-B-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.6.21 | 1F0AS-SS-B-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.6.22 | 1F0AS-SS-B-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.6.23 | 1F0AS-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.6.24 | 1F0AS-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.6.25 | 1F0AS-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.6.26 | 1F0AS-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.6.27 | 1F0AS-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.6.28 | 1F0AS-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.6.29 | 1F0AS-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.6.30 | 1F0AS-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.6.31 | 1F0AS-SS-B-04 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
A1 Electrical Room | ATS | 3.6.32 | 1F0AS-SS-B-04 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
A1 Electrical Room | ATS | 3.7.1 | 1F0AS-SS-B-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45880 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.7.2 | 1F0AS-SS-B-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45876 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.7.3 | 1F0AS-SS-B-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45873 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.7.4 | 1F0AS-SS-B-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45877 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.7.5 | 1F0AS-SS-B-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45875 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.7.6 | 1F0AS-SS-B-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45876 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.7.7 | 1F0AS-SS-B-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45880 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.7.8 | 1F0AS-SS-B-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45877 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.7.9 | 1F0AS-SS-B-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45877 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A1 Electrical Room | ATS | 3.7.10 | 1F0AS-SS-B-05 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A1 Electrical Room | ATS | 3.7.11 | 1F0AS-SS-B-05 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A1 Electrical Room | ATS | 3.7.12 | 1F0AS-SS-B-05 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A1 Electrical Room | ATS | 3.7.13 | 1F0AS-SS-B-05 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.7.14 | 1F0AS-SS-B-05 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.7.15 | 1F0AS-SS-B-05 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.7.16 | 1F0AS-SS-B-05 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.7.17 | 1F0AS-SS-B-05 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.7.18 | 1F0AS-SS-B-05 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.7.19 | 1F0AS-SS-B-05 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.7.20 | 1F0AS-SS-B-05 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.7.21 | 1F0AS-SS-B-05 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.7.22 | 1F0AS-SS-B-05 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.7.23 | 1F0AS-SS-B-05 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.7.24 | 1F0AS-SS-B-05 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.7.25 | 1F0AS-SS-B-05 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.7.26 | 1F0AS-SS-B-05 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.7.27 | 1F0AS-SS-B-05 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.7.28 | 1F0AS-SS-B-05 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.7.29 | 1F0AS-SS-B-05 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.7.30 | 1F0AS-SS-B-05 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.7.31 | 1F0AS-SS-B-05 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A1 Electrical Room | ATS | 3.7.32 | 1F0AS-SS-B-05 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.7.33 | 1F0AS-SS-B-05 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.7.34 | 1F0AS-SS-B-05 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A1 Electrical Room | ATS | 3.7.35 | 1F0AS-SS-B-05 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
A1 Electrical Room | ATS | 3.7.36 | 1F0AS-SS-B-05 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
A1 Electrical Room | ATS | 3.7.37 | 1F0AS-SS-B-05 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
A1 Electrical Room | ATS | 3.7.38 | 1F0AS-SS-B-05 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
A2 Electrical Room | ATS | 4.1.1 | 1F0AS-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.1.2 | 1F0AS-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45869 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.1.3 | 1F0AS-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.1.4 | 1F0AS-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45860 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.1.5 | 1F0AS-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.1.6 | 1F0AS-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.1.7 | 1F0AS-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45867 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.1.8 | 1F0AS-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45867 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.1.9 | 1F0AS-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45873 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.1.10 | 1F0AS-SS-C-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A2 Electrical Room | ATS | 4.1.11 | 1F0AS-SS-C-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A2 Electrical Room | ATS | 4.1.12 | 1F0AS-SS-C-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A2 Electrical Room | ATS | 4.1.13 | 1F0AS-SS-C-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A2 Electrical Room | ATS | 4.1.14 | 1F0AS-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.1.15 | 1F0AS-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.1.16 | 1F0AS-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.1.17 | 1F0AS-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.1.18 | 1F0AS-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.1.19 | 1F0AS-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.1.20 | 1F0AS-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.1.21 | 1F0AS-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.1.22 | 1F0AS-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.1.23 | 1F0AS-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.1.24 | 1F0AS-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.1.25 | 1F0AS-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.1.26 | 1F0AS-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.1.27 | 1F0AS-SS-C-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.1.28 | 1F0AS-SS-C-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.1.29 | 1F0AS-SS-C-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.1.30 | 1F0AS-SS-C-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.1.31 | 1F0AS-SS-C-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.1.32 | 1F0AS-SS-C-01 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 1 |  | 1.25 | 0 | 1.25 | COMPLETED |  |  | Transformer
A2 Electrical Room | ATS | 4.1.33 | 1F0AS-SS-C-01 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 1 |  | 1.25 | 0 | 1.25 | COMPLETED |  |  | Transformer
A2 Electrical Room | ATS | 4.1.34 | 1F0AS-SS-C-01 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
A2 Electrical Room | ATS | 4.2.1 | 1F0AS-SS-C-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45869 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.2.2 | 1F0AS-SS-C-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.2.3 | 1F0AS-SS-C-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45867 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.2.4 | 1F0AS-SS-C-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45887 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.2.5 | 1F0AS-SS-C-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45867 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.2.6 | 1F0AS-SS-C-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.2.7 | 1F0AS-SS-C-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.2.8 | 1F0AS-SS-C-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.2.9 | 1F0AS-SS-C-02 | Bus Duct - Low Voltage (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Bus Duct
A2 Electrical Room | ATS | 4.2.10 | 1F0AS-SS-C-02 | Bus Duct - Low Voltage (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Bus Duct
A2 Electrical Room | ATS | 4.2.11 | 1F0AS-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.2.12 | 1F0AS-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.2.13 | 1F0AS-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.1 | 1F0AS-SS-C-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.3.2 | 1F0AS-SS-C-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45887 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.3.3 | 1F0AS-SS-C-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45867 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.3.4 | 1F0AS-SS-C-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.3.5 | 1F0AS-SS-C-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.3.6 | 1F0AS-SS-C-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45880 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.3.7 | 1F0AS-SS-C-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45867 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.3.8 | 1F0AS-SS-C-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.3.9 | 1F0AS-SS-C-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.3.10 | 1F0AS-SS-C-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A2 Electrical Room | ATS | 4.3.11 | 1F0AS-SS-C-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A2 Electrical Room | ATS | 4.3.12 | 1F0AS-SS-C-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A2 Electrical Room | ATS | 4.3.13 | 1F0AS-SS-C-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A2 Electrical Room | ATS | 4.3.14 | 1F0AS-SS-C-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A2 Electrical Room | ATS | 4.3.15 | 1F0AS-SS-C-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A2 Electrical Room | ATS | 4.3.16 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.17 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.18 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.19 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.20 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.21 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.22 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.23 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.24 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.25 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.26 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.27 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.28 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.29 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.30 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.31 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.32 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.33 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.34 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.35 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.36 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.37 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.38 | 1F0AS-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.3.39 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.40 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.41 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.42 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.43 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.44 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.45 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.46 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.47 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.48 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.49 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.50 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.51 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.52 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.53 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.54 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.55 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.56 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.57 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.58 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.3.59 | 1F0AS-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.4.1 | 1F0AS-SS-C-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.4.2 | 1F0AS-SS-C-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.4.3 | 1F0AS-SS-C-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.4.4 | 1F0AS-SS-C-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.4.5 | 1F0AS-SS-C-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.4.6 | 1F0AS-SS-C-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45866 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.4.7 | 1F0AS-SS-C-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.4.8 | 1F0AS-SS-C-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.4.9 | 1F0AS-SS-C-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.4.10 | 1F0AS-SS-C-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
A2 Electrical Room | ATS | 4.4.11 | 1F0AS-SS-C-04 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A2 Electrical Room | ATS | 4.4.12 | 1F0AS-SS-C-04 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
A2 Electrical Room | ATS | 4.4.13 | 1F0AS-SS-C-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.4.14 | 1F0AS-SS-C-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.4.15 | 1F0AS-SS-C-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.4.16 | 1F0AS-SS-C-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
A2 Electrical Room | ATS | 4.4.17 | 1F0AS-SS-C-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.4.18 | 1F0AS-SS-C-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.4.19 | 1F0AS-SS-C-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
A2 Electrical Room | ATS | 4.4.20 | 1F0AS-SS-C-04 | Bus Duct - Low Voltage (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Bus Duct
E1 Electrical Room | ATS | 5.1.1 | 1F0EL-SS-A-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.1.2 | 1F0EL-SS-A-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45860 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.1.3 | 1F0EL-SS-A-01 | Panelboard - Low Voltage | [5 empty] | FALSE | 45911 |  | 1 |  | 1 | 0 | 1 | COMPLETED |  |  | Panelboard
E1 Electrical Room | ATS | 5.1.4 | 1F0EL-SS-A-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.1.5 | 1F0EL-SS-A-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.6 | 1F0EL-SS-A-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.7 | 1F0EL-SS-A-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.8 | 1F0EL-SS-A-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.9 | 1F0EL-SS-A-01 | Bus Duct - Low Voltage (IR/DLRO) | [5 empty] | FALSE | 45933 |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | Bus Duct
E1 Electrical Room | ATS | 5.1.10 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.11 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.12 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.13 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.14 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.15 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.16 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.17 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.18 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.19 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.20 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.21 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.22 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.23 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.24 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.25 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.26 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.27 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.28 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.29 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.30 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.31 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.32 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.33 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.34 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.35 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.36 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.37 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.38 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.39 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.1.40 | 1F0EL-SS-A-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.1 | 1F0EL-SS-A-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45860 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.2.2 | 1F0EL-SS-A-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.2.3 | 1F0EL-SS-A-02 | Bus Duct - Low Voltage (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Bus Duct
E1 Electrical Room | ATS | 5.2.4 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.5 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.6 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.7 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.8 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.9 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.10 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.11 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.12 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.13 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.14 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.15 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.16 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.17 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.18 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.19 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.20 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.21 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.22 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.23 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.24 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.25 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.26 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.27 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.28 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.29 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.30 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.31 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.32 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.33 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.34 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.35 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.2.36 | 1F0EL-SS-A-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.1 | 1F0EL-SS-A-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.3.2 | 1F0EL-SS-A-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45860 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.3.3 | 1F0EL-SS-A-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45864 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.3.4 | 1F0EL-SS-A-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45864 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.3.5 | 1F0EL-SS-A-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45860 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.3.6 | 1F0EL-SS-A-03 | Bus Duct - Low Voltage (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Bus Duct
E1 Electrical Room | ATS | 5.3.7 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.8 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.9 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.10 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.11 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.12 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.13 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.14 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.15 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.16 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.17 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.18 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.19 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.20 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.21 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.22 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.23 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.24 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.25 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.26 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.27 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.3.28 | 1F0EL-SS-A-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.4.1 | 1F0EL-SS-A-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.4.2 | 1F0EL-SS-A-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45859 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.4.3 | 1F0EL-SS-A-04 | Bus Duct - Low Voltage (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Bus Duct
E1 Electrical Room | ATS | 5.4.4 | 1F0EL-SS-A-04 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.4.5 | 1F0EL-SS-A-04 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.4.6 | 1F0EL-SS-A-04 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.4.7 | 1F0EL-SS-A-04 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.4.8 | 1F0EL-SS-A-04 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.4.9 | 1F0EL-SS-A-04 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.4.10 | 1F0EL-SS-A-04 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.4.11 | 1F0EL-SS-A-04 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.4.12 | 1F0EL-SS-A-04 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.4.13 | 1F0EL-SS-A-04 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.4.14 | 1F0EL-SS-A-04 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.4.15 | 1F0EL-SS-A-04 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.4.16 | 1F0EL-SS-A-04 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.4.17 | 1F0EL-SS-A-04 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.4.18 | 1F0EL-SS-A-04 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.4.19 | 1F0EL-SS-A-04 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.4.20 | 1F0EL-SS-A-04 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.4.21 | 1F0EL-SS-A-04 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.1 | 1F0EL-SS-B-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.5.2 | 1F0EL-SS-B-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45866 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.5.3 | 1F0EL-SS-B-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45860 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.5.4 | 1F0EL-SS-B-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45859 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.5.5 | 1F0EL-SS-B-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45859 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.5.6 | 1F0EL-SS-B-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
E1 Electrical Room | ATS | 5.5.7 | 1F0EL-SS-B-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.5.8 | 1F0EL-SS-B-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.5.9 | 1F0EL-SS-B-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.5.10 | 1F0EL-SS-B-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.5.11 | 1F0EL-SS-B-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.5.12 | 1F0EL-SS-B-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.5.13 | 1F0EL-SS-B-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.14 | 1F0EL-SS-B-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.15 | 1F0EL-SS-B-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.16 | 1F0EL-SS-B-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.17 | 1F0EL-SS-B-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.18 | 1F0EL-SS-B-01 | Bus Duct - Low Voltage (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Bus Duct
E1 Electrical Room | ATS | 5.5.19 | 1F0EL-SS-B-01 | Bus Duct - Low Voltage (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Bus Duct
E1 Electrical Room | ATS | 5.5.20 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.21 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.22 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.23 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.24 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.25 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.26 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.27 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.28 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.29 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.30 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.31 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.32 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.33 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.34 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.35 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.36 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.37 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.38 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.39 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.40 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.41 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.42 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.43 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.44 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.45 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.46 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.47 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.48 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.49 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.50 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.51 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.52 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.53 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.54 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.5.55 | 1F0EL-SS-B-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.6.1 | 1F0EL-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.6.2 | 1F0EL-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45860 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.6.3 | 1F0EL-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45860 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.6.4 | 1F0EL-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45859 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.6.5 | 1F0EL-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.6.6 | 1F0EL-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45860 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.6.7 | 1F0EL-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.6.8 | 1F0EL-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45861 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.6.9 | 1F0EL-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45860 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.6.10 | 1F0EL-SS-B-02 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | Distribution Board
E1 Electrical Room | ATS | 5.6.11 | 1F0EL-SS-B-02 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | Distribution Board
E1 Electrical Room | ATS | 5.6.12 | 1F0EL-SS-B-02 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | Distribution Board
E1 Electrical Room | ATS | 5.6.13 | 1F0EL-SS-B-02 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | Distribution Board
E1 Electrical Room | ATS | 5.6.14 | 1F0EL-SS-B-02 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
E1 Electrical Room | ATS | 5.6.15 | 1F0EL-SS-B-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 1 |  | 1 | 0 | 1 | COMPLETED |  |  | Panelboard
E1 Electrical Room | ATS | 5.6.16 | 1F0EL-SS-B-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 1 |  | 1 | 0 | 1 | COMPLETED |  |  | Panelboard
E1 Electrical Room | ATS | 5.6.17 | 1F0EL-SS-B-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 1 |  | 1 | 0 | 1 | COMPLETED |  |  | Panelboard
E1 Electrical Room | ATS | 5.6.18 | 1F0EL-SS-B-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 1 |  | 1 | 0 | 1 | COMPLETED |  |  | Panelboard
E1 Electrical Room | ATS | 5.6.19 | 1F0EL-SS-B-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 1 |  | 1 | 0 | 1 | COMPLETED |  |  | Panelboard
E1 Electrical Room | ATS | 5.6.20 | 1F0EL-SS-B-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 1 |  | 1 | 0 | 1 | COMPLETED |  |  | Panelboard
E1 Electrical Room | ATS | 5.6.21 | 1F0EL-SS-B-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 1 |  | 1 | 0 | 1 | COMPLETED |  |  | Panelboard
E1 Electrical Room | ATS | 5.6.22 | 1F0EL-SS-B-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 1 |  | 1 | 0 | 1 | COMPLETED |  |  | Panelboard
E1 Electrical Room | ATS | 5.6.23 | 1F0EL-SS-B-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 1 |  | 1 | 0 | 1 | COMPLETED |  |  | Panelboard
E1 Electrical Room | ATS | 5.6.24 | 1F0EL-SS-B-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 1 |  | 1 | 0 | 1 | COMPLETED |  |  | Panelboard
E1 Electrical Room | ATS | 5.6.25 | 1F0EL-SS-B-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.6.26 | 1F0EL-SS-B-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.6.27 | 1F0EL-SS-B-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.6.28 | 1F0EL-SS-B-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.6.29 | 1F0EL-SS-B-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.6.30 | 1F0EL-SS-B-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.6.31 | 1F0EL-SS-B-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.6.32 | 1F0EL-SS-B-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.6.33 | 1F0EL-SS-B-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.6.34 | 1F0EL-SS-B-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.6.35 | 1F0EL-SS-B-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.6.36 | 1F0EL-SS-B-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.6.37 | 1F0EL-SS-B-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.6.38 | 1F0EL-SS-B-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.6.39 | 1F0EL-SS-B-02 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 1 |  | 1.25 | 0 | 1.25 | COMPLETED |  |  | Transformer
E1 Electrical Room | ATS | 5.6.40 | 1F0EL-SS-B-02 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 1 |  | 1.25 | 0 | 1.25 | COMPLETED |  |  | Transformer
E1 Electrical Room | ATS | 5.7.1 | 1F0EL-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.7.2 | 1F0EL-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45867 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.7.3 | 1F0EL-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.7.4 | 1F0EL-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45859 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.7.5 | 1F0EL-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45859 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.7.6 | 1F0EL-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45861 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.7.7 | 1F0EL-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45870 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.7.8 | 1F0EL-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45860 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.7.9 | 1F0EL-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45861 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.7.10 | 1F0EL-SS-B-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | Distribution Board
E1 Electrical Room | ATS | 5.7.11 | 1F0EL-SS-B-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | Distribution Board
E1 Electrical Room | ATS | 5.7.12 | 1F0EL-SS-B-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | Distribution Board
E1 Electrical Room | ATS | 5.7.13 | 1F0EL-SS-B-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
E1 Electrical Room | ATS | 5.7.14 | 1F0EL-SS-B-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
E1 Electrical Room | ATS | 5.7.15 | 1F0EL-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.7.16 | 1F0EL-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.7.17 | 1F0EL-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.7.18 | 1F0EL-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.7.19 | 1F0EL-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.7.20 | 1F0EL-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.7.21 | 1F0EL-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.7.22 | 1F0EL-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.7.23 | 1F0EL-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.7.24 | 1F0EL-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.7.25 | 1F0EL-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.7.26 | 1F0EL-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.7.27 | 1F0EL-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.7.28 | 1F0EL-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.7.29 | 1F0EL-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.7.30 | 1F0EL-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.7.31 | 1F0EL-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.7.32 | 1F0EL-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.7.33 | 1F0EL-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.7.34 | 1F0EL-SS-B-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.7.35 | 1F0EL-SS-B-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.7.36 | 1F0EL-SS-B-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.7.37 | 1F0EL-SS-B-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.7.38 | 1F0EL-SS-B-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.7.39 | 1F0EL-SS-B-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.7.40 | 1F0EL-SS-B-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.7.41 | 1F0EL-SS-B-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.7.42 | 1F0EL-SS-B-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.7.43 | 1F0EL-SS-B-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.7.44 | 1F0EL-SS-B-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.7.45 | 1F0EL-SS-B-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.7.46 | 1F0EL-SS-B-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.7.47 | 1F0EL-SS-B-03 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 1 |  | 1.25 | 0 | 1.25 | COMPLETED |  |  | Transformer
E1 Electrical Room | ATS | 5.7.48 | 1F0EL-SS-B-03 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 1 |  | 1.25 | 0 | 1.25 | COMPLETED |  |  | Transformer
E1 Electrical Room | ATS | 5.7.49 | 1F0EL-SS-B-03 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 1 |  | 1.25 | 0 | 1.25 | COMPLETED |  |  | Transformer
E1 Electrical Room | ATS | 5.7.50 | 1F0EL-SS-B-03 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
E1 Electrical Room | ATS | 5.7.51 | 1F0EL-SS-B-03 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
E1 Electrical Room | ATS | 5.7.52 | 1F0EL-SS-B-03 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
E1 Electrical Room | ATS | 5.8.1 | 1F0EL-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.8.2 | 1F0EL-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45882 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.8.3 | 1F0EL-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45863 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.8.4 | 1F0EL-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45863 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.8.5 | 1F0EL-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45860 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.8.6 | 1F0EL-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45860 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.8.7 | 1F0EL-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45860 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.8.8 | 1F0EL-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45860 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.8.9 | 1F0EL-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45860 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.8.10 | 1F0EL-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45864 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.8.11 | 1F0EL-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45864 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.8.12 | 1F0EL-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45856 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.8.13 | 1F0EL-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45854 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E1 Electrical Room | ATS | 5.8.14 | 1F0EL-SS-B-04 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | Distribution Board
E1 Electrical Room | ATS | 5.8.15 | 1F0EL-SS-B-04 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | Distribution Board
E1 Electrical Room | ATS | 5.8.16 | 1F0EL-SS-B-04 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
E1 Electrical Room | ATS | 5.8.17 | 1F0EL-SS-B-04 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
E1 Electrical Room | ATS | 5.8.18 | 1F0EL-SS-B-04 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
E1 Electrical Room | ATS | 5.8.19 | 1F0EL-SS-B-04 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
E1 Electrical Room | ATS | 5.8.20 | 1F0EL-SS-B-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.8.21 | 1F0EL-SS-B-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.8.22 | 1F0EL-SS-B-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.8.23 | 1F0EL-SS-B-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.8.24 | 1F0EL-SS-B-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.8.25 | 1F0EL-SS-B-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E1 Electrical Room | ATS | 5.8.26 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.27 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.28 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.29 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.30 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.31 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.32 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.33 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.34 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.35 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.36 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.37 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.38 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.39 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.40 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.41 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.42 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.43 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.44 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.45 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.46 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.47 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E1 Electrical Room | ATS | 5.8.48 | 1F0EL-SS-B-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.1.1 | 1F0EL-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.1.2 | 1F0EL-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45890 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.1.3 | 1F0EL-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45887 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.1.4 | 1F0EL-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45861 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.1.5 | 1F0EL-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45887 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.1.6 | 1F0EL-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45861 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.1.7 | 1F0EL-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45864 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.1.8 | 1F0EL-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45862 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.1.9 | 1F0EL-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45874 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.1.10 | 1F0EL-SS-C-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | Distribution Board
E2 Electrical Room | ATS | 6.1.11 | 1F0EL-SS-C-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | Distribution Board
E2 Electrical Room | ATS | 6.1.12 | 1F0EL-SS-C-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | Distribution Board
E2 Electrical Room | ATS | 6.1.13 | 1F0EL-SS-C-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | Distribution Board
E2 Electrical Room | ATS | 6.1.14 | 1F0EL-SS-C-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
E2 Electrical Room | ATS | 6.1.15 | 1F0EL-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 1 |  | 1 | 0 | 1 | COMPLETED |  |  | Panelboard
E2 Electrical Room | ATS | 6.1.16 | 1F0EL-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 1 |  | 1 | 0 | 1 | COMPLETED |  |  | Panelboard
E2 Electrical Room | ATS | 6.1.17 | 1F0EL-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.1.18 | 1F0EL-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.1.19 | 1F0EL-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.1.20 | 1F0EL-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.1.21 | 1F0EL-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.1.22 | 1F0EL-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.1.23 | 1F0EL-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.1.24 | 1F0EL-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.1.25 | 1F0EL-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.1.26 | 1F0EL-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.1.27 | 1F0EL-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.1.28 | 1F0EL-SS-C-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.1.29 | 1F0EL-SS-C-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.1.30 | 1F0EL-SS-C-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.1.31 | 1F0EL-SS-C-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.1.32 | 1F0EL-SS-C-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.1.33 | 1F0EL-SS-C-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.1.34 | 1F0EL-SS-C-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.1.35 | 1F0EL-SS-C-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.1.36 | 1F0EL-SS-C-01 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 1 |  | 1.25 | 0 | 1.25 | COMPLETED |  |  | Transformer
E2 Electrical Room | ATS | 6.1.37 | 1F0EL-SS-C-01 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 1 |  | 1.25 | 0 | 1.25 | COMPLETED |  |  | Transformer
E2 Electrical Room | ATS | 6.2.1 | 1F0EL-SS-C-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.2.2 | 1F0EL-SS-C-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45864 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.2.3 | 1F0EL-SS-C-02 | Bus Duct - Low Voltage (IR/DLRO) | [5 empty] | FALSE |  |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | Bus Duct
E2 Electrical Room | ATS | 6.2.4 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.5 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.6 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.7 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.8 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.9 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.10 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.11 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.12 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.13 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.14 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.15 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.16 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.17 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.18 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.19 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.20 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.21 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.22 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.23 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.24 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.25 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.26 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.27 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.28 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.29 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.30 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.31 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.32 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.33 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.34 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.35 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.36 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.2.37 | 1F0EL-SS-C-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.1 | 1F0EL-SS-C-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.3.2 | 1F0EL-SS-C-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45864 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.3.3 | 1F0EL-SS-C-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.3.4 | 1F0EL-SS-C-03 | Bus Duct - Low Voltage (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Bus Duct
E2 Electrical Room | ATS | 6.3.5 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.6 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.7 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.8 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.9 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.10 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.11 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.12 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.13 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.14 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.15 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.16 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.17 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.18 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.19 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.20 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.21 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.22 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.23 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.24 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.25 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.26 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.27 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.28 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.29 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.30 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.31 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.32 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.33 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.34 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.35 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.36 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.37 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.38 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.39 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.40 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.41 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.42 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.43 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.44 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.45 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.46 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.47 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.48 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.49 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.50 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.51 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.52 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.53 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.54 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.55 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.56 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.3.57 | 1F0EL-SS-C-03 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.4.1 | 1F0EL-SS-D-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.4.2 | 1F0EL-SS-D-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45864 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.4.3 | 1F0EL-SS-D-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45864 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.4.4 | 1F0EL-SS-D-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45865 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.4.5 | 1F0EL-SS-D-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45864 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.4.6 | 1F0EL-SS-D-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.4.7 | 1F0EL-SS-D-02 | Bus Duct - Low Voltage (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Bus Duct
E2 Electrical Room | ATS | 6.4.8 | 1F0EL-SS-D-02 | Bus Duct - Low Voltage (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Bus Duct
E2 Electrical Room | ATS | 6.4.9 | 1F0EL-SS-D-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.4.10 | 1F0EL-SS-D-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.4.11 | 1F0EL-SS-D-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.4.12 | 1F0EL-SS-D-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.4.13 | 1F0EL-SS-D-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.4.14 | 1F0EL-SS-D-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.4.15 | 1F0EL-SS-D-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.4.16 | 1F0EL-SS-D-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.4.17 | 1F0EL-SS-D-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.4.18 | 1F0EL-SS-D-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.4.19 | 1F0EL-SS-D-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.4.20 | 1F0EL-SS-D-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.4.21 | 1F0EL-SS-D-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.4.22 | 1F0EL-SS-D-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.4.23 | 1F0EL-SS-D-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.4.24 | 1F0EL-SS-D-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.4.25 | 1F0EL-SS-D-02 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.1 | 1F0EL-SS-D-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.5.2 | 1F0EL-SS-D-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45887 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.5.3 | 1F0EL-SS-D-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45887 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.5.4 | 1F0EL-SS-D-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45870 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.5.5 | 1F0EL-SS-D-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45864 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.5.6 | 1F0EL-SS-D-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45896 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.5.7 | 1F0EL-SS-D-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.5.8 | 1F0EL-SS-D-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.5.9 | 1F0EL-SS-D-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45887 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.5.10 | 1F0EL-SS-D-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45874 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.5.11 | 1F0EL-SS-D-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45870 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.5.12 | 1F0EL-SS-D-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | Distribution Board
E2 Electrical Room | ATS | 6.5.13 | 1F0EL-SS-D-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | Distribution Board
E2 Electrical Room | ATS | 6.5.14 | 1F0EL-SS-D-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | Distribution Board
E2 Electrical Room | ATS | 6.5.15 | 1F0EL-SS-D-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 1 |  | 1 | 0 | 1 | COMPLETED |  |  | Panelboard
E2 Electrical Room | ATS | 6.5.16 | 1F0EL-SS-D-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.5.17 | 1F0EL-SS-D-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.5.18 | 1F0EL-SS-D-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.5.19 | 1F0EL-SS-D-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.5.20 | 1F0EL-SS-D-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.5.21 | 1F0EL-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.22 | 1F0EL-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.23 | 1F0EL-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.24 | 1F0EL-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.25 | 1F0EL-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.26 | 1F0EL-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.27 | 1F0EL-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.28 | 1F0EL-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.29 | 1F0EL-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.30 | 1F0EL-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.31 | 1F0EL-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.32 | 1F0EL-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.33 | 1F0EL-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.34 | 1F0EL-SS-D-01 | Bus Duct - Low Voltage (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Bus Duct
E2 Electrical Room | ATS | 6.5.35 | 1F0EL-SS-D-01 | Bus Duct - Low Voltage (IR/DLRO) | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Bus Duct
E2 Electrical Room | ATS | 6.5.36 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.37 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.38 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.39 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.40 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.41 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.42 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.43 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.44 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.45 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.46 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.47 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.48 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.49 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.50 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.51 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.52 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.53 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.54 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.55 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.56 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.57 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.58 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.59 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.60 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.61 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.62 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.63 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.64 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.65 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.66 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.67 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.68 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.69 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.70 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.71 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.5.72 | 1F0EL-SS-D-01 | Circuit Breaker LV - Bus Duct (Secondary) | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.6.1 | 1F0EL-SS-D-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.6.2 | 1F0EL-SS-D-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45869 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.6.3 | 1F0EL-SS-D-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45863 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.6.4 | 1F0EL-SS-D-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45862 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.6.5 | 1F0EL-SS-D-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.6.6 | 1F0EL-SS-D-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45861 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.6.7 | 1F0EL-SS-D-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45861 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.6.8 | 1F0EL-SS-D-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45861 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.6.9 | 1F0EL-SS-D-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE | 45862 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
E2 Electrical Room | ATS | 6.6.10 | 1F0EL-SS-D-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | Distribution Board
E2 Electrical Room | ATS | 6.6.11 | 1F0EL-SS-D-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 1 |  | 4 | 0 | 4 | COMPLETED |  |  | Distribution Board
E2 Electrical Room | ATS | 6.6.12 | 1F0EL-SS-D-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
E2 Electrical Room | ATS | 6.6.13 | 1F0EL-SS-D-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
E2 Electrical Room | ATS | 6.6.14 | 1F0EL-SS-D-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 1 |  | 1 | 0 | 1 | COMPLETED |  |  | Panelboard
E2 Electrical Room | ATS | 6.6.15 | 1F0EL-SS-D-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 1 |  | 1 | 0 | 1 | COMPLETED |  |  | Panelboard
E2 Electrical Room | ATS | 6.6.16 | 1F0EL-SS-D-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 1 |  | 1 | 0 | 1 | COMPLETED |  |  | Panelboard
E2 Electrical Room | ATS | 6.6.17 | 1F0EL-SS-D-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 1 |  | 1 | 0 | 1 | COMPLETED |  |  | Panelboard
E2 Electrical Room | ATS | 6.6.18 | 1F0EL-SS-D-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.6.19 | 1F0EL-SS-D-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.6.20 | 1F0EL-SS-D-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.6.21 | 1F0EL-SS-D-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.6.22 | 1F0EL-SS-D-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.6.23 | 1F0EL-SS-D-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.6.24 | 1F0EL-SS-D-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.6.25 | 1F0EL-SS-D-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.6.26 | 1F0EL-SS-D-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.6.27 | 1F0EL-SS-D-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.6.28 | 1F0EL-SS-D-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.6.29 | 1F0EL-SS-D-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.6.30 | 1F0EL-SS-D-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.6.31 | 1F0EL-SS-D-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.6.32 | 1F0EL-SS-D-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.6.33 | 1F0EL-SS-D-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
E2 Electrical Room | ATS | 6.6.34 | 1F0EL-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.6.35 | 1F0EL-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.6.36 | 1F0EL-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.6.37 | 1F0EL-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.6.38 | 1F0EL-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.6.39 | 1F0EL-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.6.40 | 1F0EL-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.6.41 | 1F0EL-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.6.42 | 1F0EL-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.6.43 | 1F0EL-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.6.44 | 1F0EL-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
E2 Electrical Room | ATS | 6.6.45 | 1F0EL-SS-D-03 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
E2 Electrical Room | ATS | 6.6.46 | 1F0EL-SS-D-03 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
E2 Electrical Room | ATS | 6.6.47 | 1F0EL-SS-D-03 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
E2 Electrical Room | ATS | 6.6.48 | 1F0EL-SS-D-03 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
E2 Electrical Room | ATS | 6.7.1 | Equip Grounding P-T-P | Ground Resistance Test - Two-Point | [5 empty] | FALSE |  |  | 1 |  | 0.3 | 0 | 0.3 | COMPLETED |  |  | Grounding
E2 Electrical Room | ATS | 6.7.2 | Equip Grounding P-T-P | Ground Resistance Test - Two-Point | [5 empty] | FALSE |  |  | 1 |  | 0.3 | 0 | 0.3 | COMPLETED |  |  | Grounding
E2 Electrical Room | ATS | 6.7.3 | Equip Grounding P-T-P | Ground Resistance Test - Two-Point | [5 empty] | FALSE |  |  | 0 |  | 0.3 | 0.3 | 0.3 |  |  |  | Grounding
E2 Electrical Room | ATS | 6.7.4 | Equip Grounding P-T-P | Ground Resistance Test - Two-Point | [5 empty] | FALSE |  |  | 0 |  | 0.3 | 0.3 | 0.3 |  |  |  | Grounding
E2 Electrical Room | ATS | 6.7.5 | Equip Grounding P-T-P | Ground Resistance Test - Two-Point | [5 empty] | FALSE |  |  | 0 |  | 0.3 | 0.3 | 0.3 |  |  |  | Grounding
E2 Electrical Room | ATS | 6.7.6 | Equip Grounding P-T-P | Ground Resistance Test - Two-Point | [5 empty] | FALSE |  |  | 0 |  | 0.3 | 0.3 | 0.3 |  |  |  | Grounding
E2 Electrical Room | ATS | 6.7.7 | Equip Grounding P-T-P | Ground Resistance Test - Two-Point | [5 empty] | FALSE |  |  | 0 |  | 0.3 | 0.3 | 0.3 |  |  |  | Grounding
E2 Electrical Room | ATS | 6.7.8 | Equip Grounding P-T-P | Ground Resistance Test - Two-Point | [5 empty] | FALSE |  |  | 0 |  | 0.3 | 0.3 | 0.3 |  |  |  | Grounding
E2 Electrical Room | ATS | 6.7.9 | Equip Grounding P-T-P | Ground Resistance Test - Two-Point | [5 empty] | FALSE |  |  | 0 |  | 0.3 | 0.3 | 0.3 |  |  |  | Grounding
F1 Electrical Room | ATS | 6.1.1 | 1F0FO-SS-A-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45894 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.1.2 | 1F0FO-SS-A-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45894 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.1.3 | 1F0FO-SS-A-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45894 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.1.4 | 1F0FO-SS-A-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45894 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.1.5 | 1F0FO-SS-A-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45894 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.1.6 | 1F0FO-SS-A-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45894 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.1.7 | 1F0FO-SS-A-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45894 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.1.8 | 1F0FO-SS-A-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45894 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.1.9 | 1F0FO-SS-A-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45894 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.2.1 | 1F0FO-SS-A-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45891 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.2.2 | 1F0FO-SS-A-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45888 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.2.3 | 1F0FO-SS-A-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45889 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.2.4 | 1F0FO-SS-A-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45888 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.2.5 | 1F0FO-SS-A-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45889 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.2.6 | 1F0FO-SS-A-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45888 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.2.7 | 1F0FO-SS-A-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45888 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.2.8 | 1F0FO-SS-A-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45888 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.2.9 | 1F0FO-SS-A-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45888 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.2.10 | 1F0FO-SS-A-02 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F1 Electrical Room | ATS | 6.2.11 | 1F0FO-SS-A-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.2.12 | 1F0FO-SS-A-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.2.13 | 1F0FO-SS-A-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.2.14 | 1F0FO-SS-A-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.2.15 | 1F0FO-SS-A-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.2.16 | 1F0FO-SS-A-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.2.17 | 1F0FO-SS-A-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.2.18 | 1F0FO-SS-A-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.2.19 | 1F0FO-SS-A-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.2.20 | 1F0FO-SS-A-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F1 Electrical Room | ATS | 6.2.21 | 1F0FO-SS-A-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F1 Electrical Room | ATS | 6.2.22 | 1F0FO-SS-A-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F1 Electrical Room | ATS | 6.2.23 | 1F0FO-SS-A-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F1 Electrical Room | ATS | 6.2.24 | 1F0FO-SS-A-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F1 Electrical Room | ATS | 6.3.1 | 1F0FO-SS-A-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45888 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.3.2 | 1F0FO-SS-A-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45896 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.3.3 | 1F0FO-SS-A-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45882 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.3.4 | 1F0FO-SS-A-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45882 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.3.5 | 1F0FO-SS-A-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45882 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.3.6 | 1F0FO-SS-A-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45882 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.3.7 | 1F0FO-SS-A-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45882 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.3.8 | 1F0FO-SS-A-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45881 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.3.9 | 1F0FO-SS-A-03 | Circuit Breaker LV - Insulated Case (LSIG) |  |  |  | MISSING DATASHEET |  | FALSE |  | MISSING DATASHEET | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.3.10 | 1F0FO-SS-A-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F1 Electrical Room | ATS | 6.3.11 | 1F0FO-SS-A-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F1 Electrical Room | ATS | 6.3.12 | 1F0FO-SS-A-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F1 Electrical Room | ATS | 6.3.13 | 1F0FO-SS-A-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.3.14 | 1F0FO-SS-A-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.3.15 | 1F0FO-SS-A-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.3.16 | 1F0FO-SS-A-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.3.17 | 1F0FO-SS-A-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.3.18 | 1F0FO-SS-A-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.3.19 | 1F0FO-SS-A-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.3.20 | 1F0FO-SS-A-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.3.21 | 1F0FO-SS-A-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.3.22 | 1F0FO-SS-A-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.3.23 | 1F0FO-SS-A-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.3.24 | 1F0FO-SS-A-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.3.25 | 1F0FO-SS-A-03 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F1 Electrical Room | ATS | 6.3.26 | 1F0FO-SS-A-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F1 Electrical Room | ATS | 6.3.27 | 1F0FO-SS-A-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F1 Electrical Room | ATS | 6.3.28 | 1F0FO-SS-A-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F1 Electrical Room | ATS | 6.3.29 | 1F0FO-SS-A-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F1 Electrical Room | ATS | 6.3.30 | 1F0FO-SS-A-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F1 Electrical Room | ATS | 6.3.31 | 1F0FO-SS-A-03 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
F1 Electrical Room | ATS | 6.4.1 | 1F0FO-SS-A-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45895 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.4.2 | 1F0FO-SS-A-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45882 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.4.3 | 1F0FO-SS-A-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45882 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.4.4 | 1F0FO-SS-A-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45883 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.4.5 | 1F0FO-SS-A-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45882 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.4.6 | 1F0FO-SS-A-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45883 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.4.7 | 1F0FO-SS-A-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45883 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.4.8 | 1F0FO-SS-A-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45894 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.4.9 | 1F0FO-SS-A-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45883 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.5.1 | 1F0FO-SS-A-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45888 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.5.2 | 1F0FO-SS-A-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45881 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.5.3 | 1F0FO-SS-A-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45882 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.5.4 | 1F0FO-SS-A-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45882 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.5.5 | 1F0FO-SS-A-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45882 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.5.6 | 1F0FO-SS-A-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45881 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.5.7 | 1F0FO-SS-A-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45881 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.5.8 | 1F0FO-SS-A-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45881 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.5.9 | 1F0FO-SS-A-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45881 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.6.1 | 1F0FO-SS-B-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45889 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.6.2 | 1F0FO-SS-B-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45890 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.6.3 | 1F0FO-SS-B-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45890 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.6.4 | 1F0FO-SS-B-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45890 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.6.5 | 1F0FO-SS-B-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45890 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.6.6 | 1F0FO-SS-B-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45895 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.6.7 | 1F0FO-SS-B-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45890 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.6.8 | 1F0FO-SS-B-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45890 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.6.9 | 1F0FO-SS-B-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45890 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.6.10 | 1F0FO-SS-B-01 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
F1 Electrical Room | ATS | 6.6.11 | 1F0FO-SS-B-01 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
F1 Electrical Room | ATS | 6.7.1 | 1F0FO-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45890 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.7.2 | 1F0FO-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45887 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.7.3 | 1F0FO-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45889 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.7.4 | 1F0FO-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45887 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.7.5 | 1F0FO-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45887 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.7.6 | 1F0FO-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45887 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.7.7 | 1F0FO-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45887 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.7.8 | 1F0FO-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45887 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.7.9 | 1F0FO-SS-B-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45888 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.7.10 | 1F0FO-SS-B-02 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F1 Electrical Room | ATS | 6.7.11 | 1F0FO-SS-B-02 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F1 Electrical Room | ATS | 6.7.12 | 1F0FO-SS-B-02 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F1 Electrical Room | ATS | 6.7.13 | 1F0FO-SS-B-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F1 Electrical Room | ATS | 6.7.14 | 1F0FO-SS-B-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F1 Electrical Room | ATS | 6.7.15 | 1F0FO-SS-B-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F1 Electrical Room | ATS | 6.7.16 | 1F0FO-SS-B-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F1 Electrical Room | ATS | 6.7.17 | 1F0FO-SS-B-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F1 Electrical Room | ATS | 6.7.18 | 1F0FO-SS-B-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F1 Electrical Room | ATS | 6.8.1 | 1F0FO-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45890 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.8.2 | 1F0FO-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45887 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.8.3 | 1F0FO-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45889 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.8.4 | 1F0FO-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45889 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.8.5 | 1F0FO-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45884 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.8.6 | 1F0FO-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45888 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.8.7 | 1F0FO-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45887 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.8.8 | 1F0FO-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45884 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.8.9 | 1F0FO-SS-B-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45887 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.9.1 | 1F0FO-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45888 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.9.2 | 1F0FO-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45889 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.9.3 | 1F0FO-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45883 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.9.4 | 1F0FO-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45883 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.9.5 | 1F0FO-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45883 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.9.6 | 1F0FO-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45883 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.9.7 | 1F0FO-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45884 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.9.8 | 1F0FO-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45883 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.9.9 | 1F0FO-SS-B-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45883 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.10.1 | 1F0FO-SS-B-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45883 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.10.2 | 1F0FO-SS-B-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45883 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.10.3 | 1F0FO-SS-B-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45881 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.10.4 | 1F0FO-SS-B-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45881 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.10.5 | 1F0FO-SS-B-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45881 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.10.6 | 1F0FO-SS-B-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45881 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.10.7 | 1F0FO-SS-B-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45881 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.10.8 | 1F0FO-SS-B-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45882 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F1 Electrical Room | ATS | 6.10.9 | 1F0FO-SS-B-05 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45882 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.1.1 | 1F0FO-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45873 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.1.2 | 1F0FO-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45873 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.1.3 | 1F0FO-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45875 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.1.4 | 1F0FO-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45873 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.1.5 | 1F0FO-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45880 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.1.6 | 1F0FO-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45875 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.1.7 | 1F0FO-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45875 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.1.8 | 1F0FO-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45875 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.1.9 | 1F0FO-SS-C-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45875 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.1.10 | 1F0FO-SS-C-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.1.11 | 1F0FO-SS-C-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.1.12 | 1F0FO-SS-C-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.1.13 | 1F0FO-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.1.14 | 1F0FO-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.1.15 | 1F0FO-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.1.16 | 1F0FO-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.1.17 | 1F0FO-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.1.18 | 1F0FO-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.1.19 | 1F0FO-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.1.20 | 1F0FO-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.1.21 | 1F0FO-SS-C-01 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.1.22 | 1F0FO-SS-C-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.1.23 | 1F0FO-SS-C-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.1.24 | 1F0FO-SS-C-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.1.25 | 1F0FO-SS-C-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.1.26 | 1F0FO-SS-C-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.1.27 | 1F0FO-SS-C-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.1.28 | 1F0FO-SS-C-01 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
F2 Electrical Room | ATS | 8.1.29 | 1F0FO-SS-C-01 | Transformer - Dry Type (TTR/IR) | [5 empty] | FALSE |  |  | 0 |  | 1.25 | 1.25 | 1.25 |  |  |  | Transformer
F2 Electrical Room | ATS | 8.2.1 | 1F0FO-SS-C-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45873 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.2.2 | 1F0FO-SS-C-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45873 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.2.3 | 1F0FO-SS-C-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45873 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.2.4 | 1F0FO-SS-C-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45873 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.2.5 | 1F0FO-SS-C-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45876 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.2.6 | 1F0FO-SS-C-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45875 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.2.7 | 1F0FO-SS-C-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45875 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.2.8 | 1F0FO-SS-C-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45876 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.2.9 | 1F0FO-SS-C-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45876 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.2.10 | 1F0FO-SS-C-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45902 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.2.11 | 1F0FO-SS-C-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45875 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.2.12 | 1F0FO-SS-C-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45876 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.2.13 | 1F0FO-SS-C-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | FALSE |  |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.2.14 | 1F0FO-SS-C-02 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.2.15 | 1F0FO-SS-C-02 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.2.16 | 1F0FO-SS-C-02 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.2.17 | 1F0FO-SS-C-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.2.18 | 1F0FO-SS-C-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.2.19 | 1F0FO-SS-C-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.2.20 | 1F0FO-SS-C-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.2.21 | 1F0FO-SS-C-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.2.22 | 1F0FO-SS-C-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.2.23 | 1F0FO-SS-C-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.2.24 | 1F0FO-SS-C-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.2.25 | 1F0FO-SS-C-02 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.2.26 | 1F0FO-SS-C-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.2.27 | 1F0FO-SS-C-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.2.28 | 1F0FO-SS-C-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.2.29 | 1F0FO-SS-C-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.2.30 | 1F0FO-SS-C-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.2.31 | 1F0FO-SS-C-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.2.32 | 1F0FO-SS-C-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.2.33 | 1F0FO-SS-C-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.3.1 | 1F0FO-SS-C-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45871 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.3.2 | 1F0FO-SS-C-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45875 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.3.3 | 1F0FO-SS-C-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45873 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.3.4 | 1F0FO-SS-C-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45871 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.3.5 | 1F0FO-SS-C-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45871 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.3.6 | 1F0FO-SS-C-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45873 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.3.7 | 1F0FO-SS-C-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45873 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.3.8 | 1F0FO-SS-C-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45874 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.3.9 | 1F0FO-SS-C-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45873 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.3.10 | 1F0FO-SS-C-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.3.11 | 1F0FO-SS-C-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.3.12 | 1F0FO-SS-C-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.3.13 | 1F0FO-SS-C-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.3.14 | 1F0FO-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.3.15 | 1F0FO-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.3.16 | 1F0FO-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.3.17 | 1F0FO-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.3.18 | 1F0FO-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.3.19 | 1F0FO-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.3.20 | 1F0FO-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.3.21 | 1F0FO-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.3.22 | 1F0FO-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.3.23 | 1F0FO-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.3.24 | 1F0FO-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.3.25 | 1F0FO-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.3.26 | 1F0FO-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.3.27 | 1F0FO-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.3.28 | 1F0FO-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.3.29 | 1F0FO-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.3.30 | 1F0FO-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.3.31 | 1F0FO-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.3.32 | 1F0FO-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.3.33 | 1F0FO-SS-C-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.4.1 | 1F0FO-SS-C-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45873 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.4.2 | 1F0FO-SS-C-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45875 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.4.3 | 1F0FO-SS-C-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45871 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.4.4 | 1F0FO-SS-C-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45871 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.4.5 | 1F0FO-SS-C-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45873 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.4.6 | 1F0FO-SS-C-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45873 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.4.7 | 1F0FO-SS-C-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45876 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.4.8 | 1F0FO-SS-C-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45873 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.4.9 | 1F0FO-SS-C-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45873 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.4.10 | 1F0FO-SS-C-04 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.4.11 | 1F0FO-SS-C-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.4.12 | 1F0FO-SS-C-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.4.13 | 1F0FO-SS-C-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.4.14 | 1F0FO-SS-C-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.4.15 | 1F0FO-SS-C-04 | Panelboard - Low Voltage | [5 empty] | FALSE |  |  | 0 |  | 1 | 1 | 1 |  |  |  | Panelboard
F2 Electrical Room | ATS | 8.4.16 | 1F0FO-SS-C-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.4.17 | 1F0FO-SS-C-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.4.18 | 1F0FO-SS-C-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.4.19 | 1F0FO-SS-C-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.4.20 | 1F0FO-SS-C-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.4.21 | 1F0FO-SS-C-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.4.22 | 1F0FO-SS-C-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.4.23 | 1F0FO-SS-C-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.4.24 | 1F0FO-SS-C-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.4.25 | 1F0FO-SS-C-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.4.26 | 1F0FO-SS-C-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.5.1 | 1F0FO-SS-D-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45870 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.5.2 | 1F0FO-SS-D-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45869 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.5.3 | 1F0FO-SS-D-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45869 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.5.4 | 1F0FO-SS-D-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45870 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.5.5 | 1F0FO-SS-D-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45871 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.5.6 | 1F0FO-SS-D-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45871 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.5.7 | 1F0FO-SS-D-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45870 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.5.8 | 1F0FO-SS-D-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45870 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.5.9 | 1F0FO-SS-D-01 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45873 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.5.10 | 1F0FO-SS-D-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.5.11 | 1F0FO-SS-D-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.5.12 | 1F0FO-SS-D-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.5.13 | 1F0FO-SS-D-01 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.5.14 | 1F0FO-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.5.15 | 1F0FO-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.5.16 | 1F0FO-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.5.17 | 1F0FO-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.5.18 | 1F0FO-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.5.19 | 1F0FO-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.5.20 | 1F0FO-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.5.21 | 1F0FO-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.5.22 | 1F0FO-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.5.23 | 1F0FO-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.5.24 | 1F0FO-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.5.25 | 1F0FO-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.5.26 | 1F0FO-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.5.27 | 1F0FO-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.5.28 | 1F0FO-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.5.29 | 1F0FO-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.5.30 | 1F0FO-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.5.31 | 1F0FO-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.5.32 | 1F0FO-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.5.33 | 1F0FO-SS-D-01 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.6.1 | 1F0FO-SS-D-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45870 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.6.2 | 1F0FO-SS-D-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45871 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.6.3 | 1F0FO-SS-D-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45871 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.6.4 | 1F0FO-SS-D-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45870 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.6.5 | 1F0FO-SS-D-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45869 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.6.6 | 1F0FO-SS-D-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45869 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.6.7 | 1F0FO-SS-D-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45869 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.6.8 | 1F0FO-SS-D-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45894 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.6.9 | 1F0FO-SS-D-02 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45870 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.6.10 | 1F0FO-SS-D-02 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.6.11 | 1F0FO-SS-D-02 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.6.12 | 1F0FO-SS-D-02 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.6.13 | 1F0FO-SS-D-02 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.6.14 | 1F0FO-SS-D-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.6.15 | 1F0FO-SS-D-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.6.16 | 1F0FO-SS-D-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.6.17 | 1F0FO-SS-D-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.6.18 | 1F0FO-SS-D-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.6.19 | 1F0FO-SS-D-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.6.20 | 1F0FO-SS-D-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.6.21 | 1F0FO-SS-D-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.6.22 | 1F0FO-SS-D-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.6.23 | 1F0FO-SS-D-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.6.24 | 1F0FO-SS-D-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.6.25 | 1F0FO-SS-D-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.6.26 | 1F0FO-SS-D-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.6.27 | 1F0FO-SS-D-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.6.28 | 1F0FO-SS-D-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.6.29 | 1F0FO-SS-D-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.6.30 | 1F0FO-SS-D-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.6.31 | 1F0FO-SS-D-02 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.7.1 | 1F0FO-SS-D-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45871 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.7.2 | 1F0FO-SS-D-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45871 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.7.3 | 1F0FO-SS-D-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45894 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.7.4 | 1F0FO-SS-D-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45870 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.7.5 | 1F0FO-SS-D-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45870 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.7.6 | 1F0FO-SS-D-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45869 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.7.7 | 1F0FO-SS-D-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45869 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.7.8 | 1F0FO-SS-D-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.7.9 | 1F0FO-SS-D-03 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45869 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.7.10 | 1F0FO-SS-D-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.7.11 | 1F0FO-SS-D-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.7.12 | 1F0FO-SS-D-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.7.13 | 1F0FO-SS-D-03 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.7.14 | 1F0FO-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.7.15 | 1F0FO-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.7.16 | 1F0FO-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.7.17 | 1F0FO-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.7.18 | 1F0FO-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.7.19 | 1F0FO-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.7.20 | 1F0FO-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.7.21 | 1F0FO-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.7.22 | 1F0FO-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.7.23 | 1F0FO-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.7.24 | 1F0FO-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.7.25 | 1F0FO-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.7.26 | 1F0FO-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.7.27 | 1F0FO-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.7.28 | 1F0FO-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.7.29 | 1F0FO-SS-D-03 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.8.1 | 1F0FO-SS-D-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45869 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.8.2 | 1F0FO-SS-D-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45890 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.8.3 | 1F0FO-SS-D-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45870 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.8.4 | 1F0FO-SS-D-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.8.5 | 1F0FO-SS-D-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45869 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.8.6 | 1F0FO-SS-D-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45869 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.8.7 | 1F0FO-SS-D-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45868 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.8.8 | 1F0FO-SS-D-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45873 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.8.9 | 1F0FO-SS-D-04 | Circuit Breaker LV - Insulated Case (LSIG) | [5 empty] | TRUE | 45874 |  | 1 |  | 3 | 0 | 3 | COMPLETED |  |  | Circuit Breaker - Primary
F2 Electrical Room | ATS | 8.8.10 | 1F0FO-SS-D-04 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.8.11 | 1F0FO-SS-D-04 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.8.12 | 1F0FO-SS-D-04 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.8.13 | 1F0FO-SS-D-04 | Switchboard - Distribution LV | [5 empty] | FALSE |  |  | 0 |  | 4 | 4 | 4 |  |  |  | Distribution Board
F2 Electrical Room | ATS | 8.8.14 | 1F0FO-SS-D-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.8.15 | 1F0FO-SS-D-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.8.16 | 1F0FO-SS-D-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.8.17 | 1F0FO-SS-D-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.8.18 | 1F0FO-SS-D-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.8.19 | 1F0FO-SS-D-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.8.20 | 1F0FO-SS-D-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.8.21 | 1F0FO-SS-D-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.8.22 | 1F0FO-SS-D-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.8.23 | 1F0FO-SS-D-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.8.24 | 1F0FO-SS-D-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.8.25 | 1F0FO-SS-D-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.8.26 | 1F0FO-SS-D-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.8.27 | 1F0FO-SS-D-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary
F2 Electrical Room | ATS | 8.8.28 | 1F0FO-SS-D-04 | Circuit Breaker LV - Secondary Injection | [5 empty] | FALSE |  |  | 0 |  | 0.5 | 0.5 | 0.5 |  |  |  | Circuit Breaker - Secondary