## Scope_Labor_Rates
SCOPE LABOR RATES & BILLING CONFIGURATION
Enter rates and percentages for each scope. These values will be used in All_Tasks_Billing calculations.
SCOPE |  | RATES | TIME ADDERS (% of Total Hours) | [10 empty] | SCOPE FIXED COSTS ($ PER APPARATUS HR) |  |  | MULTIPLIER | WEIGHTED TOTALS
Scope | Total Apparatus Hours | Scope Bill Rate/Hr | Commute Bill Rate/Hr | Commute % | PM Bill Rate/Hr | PM Time % | Daily Report Bill Rate/Hr | Daily Report % | Travel Bill Rate/Hr | Travel % | Final Report Bill Rate/Hr | Final Report % | Travel Sheet Total $ | Travel $/App Hr | M&E Sheet Total $ | M&E $/App Hr | Scope Multiplier | Scope Sheet Total
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 125 | 4.3% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 150 | 2.1% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 150 | 2.1% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 150 | 3.7% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 150 | 3% | 150 | 0% | 150 | 0% | 0 | 0 | 7500 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 150 | 0.5% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 150 | 0.5% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 150 | 0.5% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 150 | 0.5% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 150 | 0% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 150 | 0% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 150 | 0% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 150 | 0% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 150 | 0% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 150 | 0% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 150 | 0% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
#VALUE! | 0 | 150 | 150 | 0% | 150 | 0% | 150 | 0% | 150 | 0% | 150 | 0% | 0 | 0 | 0 | 0 | 1 | 0
SUMMARY TOTALS
Total Apparatus Hours: | 0
Labor Rate/Hr | 0
Total Travel Fixed Costs: | 0
Total M&E Fixed Costs: | 7500
Total Project Value: | 0
INSTRUCTIONS:
2. YELLOW CELLS are for manual input:
• Total Apparatus Hours (Column B)
• Total Apparatus Hours (Column C)
• Travel Fixed Total $ (Column S)
• M&E Fixed Total $ (Column U)
• Scope Multiplier (Column Y)
3. SCOPE MULTIPLIER (Column Y) Usage:
• 1.000 = No adjustment (bill at calculated cost)
• 1.050 = 5% markup (for profit, risk, etc.)
• 0.950 = 5% discount (competitive adjustment)
4. Fixed costs are automatically allocated per apparatus hour
5. Time adders are calculated as percentages of base labor
6. Final Report % added to final billing cycle.

## PowerBI_Data
Scope | NETA_Standard | Task_ID | Task | Apparatus | Designation | Drawing | Date Due | Notes | Assessment | DATASHEET | DATE COMPLETED | NOTES2 | % COMPLETION | TASK DELAYS | Apparatus Hours | Remaining Hours | ACTUAL HOURS | STATUS | AVAILABILITY | PRIORITY | Scope_Helper | Base_Rate | Scope_Budget | Multiplier | Completion | Week_Ending | Billing_Period | Base_Labor_$ | Commute_Hrs | Commute_$ | PM_Hrs | PM_$ | Report_Hrs | Report_$ | Travel_Hrs | Travel_$ | Final_Hrs | Final_$ | Travel_Fixed_$ | ME_Fixed_$ | Total_Var_Hrs | Total_Var_$ | Total_Fixed_$ | Subtotal_$ | Total_Billable_$ | Completion_Month | Completion_Quarter | Completion_Year | Date_Bin_Week | Date_Bin_Month | Date_Bin_Quarter | Earned_Revenue | Billable_Week | Billable_Month | Revenue_Per_Hour | Completion_Status | Hours_Efficiency | Scope_Completion_Rate | Status_Priority | Status_Availability | Priority_Availability | Complete_Status_Priority | Days_Since_Completed
LAS16.PPM01 | PPM | 1.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.17 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.19 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.20 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.21 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 19.8 | 19.8 | 19.8 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.8514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8514 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.22 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.23 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.24 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.1.25 | Main Switchgear | LV Disconnect | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.25 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.26 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM01 | PPM | 1.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 6 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.1.24 | Main Switchgear | LV Disconnect | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.25 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.26 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM02 | PPM | 2.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 7 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.1.24 | Main Switchgear | LV Disconnect | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.25 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.26 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM03 | PPM | 3.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 8 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.1.24 | Main Switchgear | LV Disconnect | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.25 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.26 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM04 | PPM | 4.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 9 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.1.24 | Main Switchgear | LV Disconnect | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.25 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.26 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM05 | PPM | 5.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 10 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.1.24 | Main Switchgear | LV Disconnect | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.25 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.26 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM06 | PPM | 6.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 11 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.1.24 | Main Switchgear | LV Disconnect | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.25 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.26 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM07 | PPM | 7.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 12 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.1.24 | Main Switchgear | LV Disconnect | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.25 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.26 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM08 | PPM | 8.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 13 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.1.24 | Main Switchgear | LV Disconnect | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.25 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.26 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM09 | PPM | 9.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 14 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.1.24 | Main Switchgear | LV Disconnect | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.25 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.26 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM10 | PPM | 10.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 15 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.1.24 | Main Switchgear | LV Disconnect | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.25 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.26 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM11 | PPM | 11.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 16 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.1.24 | Main Switchgear | LV Disconnect | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.25 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.26 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM12 | PPM | 12.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 17 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.1.24 | Main Switchgear | LV Disconnect | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.25 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.26 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM13 | PPM | 13.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 18 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 19 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM14 | PPM | 14.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 19 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM14 | PPM | 14.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 19 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM14 | PPM | 14.1.24 | Main Switchgear | LV Disconnect | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 1.5 | 0 | 1.5 | COMPLETED | READY |  | 19 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 225 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 233.0625 | 233.0625 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 233.0625 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM14 | PPM | 14.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 19 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM14 | PPM | 14.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 19 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM14 | PPM | 14.2.25 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 | NOT STARTED | READY |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 | NOT STARTED - | NOT STARTED - READY |  | Not Started ¦ NOT STARTED ¦
LAS16.PPM14 | PPM | 14.2.26 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 | NOT STARTED | READY |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 | NOT STARTED - | NOT STARTED - READY |  | Not Started ¦ NOT STARTED ¦
LAS16.PPM14 | PPM | 14.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  | ON HOLD |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  | ON HOLD |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM14 | PPM | 14.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 19 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 20 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM15 | PPM | 15.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 20 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM15 | PPM | 15.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 20 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM15 | PPM | 15.1.24 | Main Switchgear | LV Disconnect | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 1.5 | 0 | 1.5 | COMPLETED | READY |  | 20 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 225 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 233.0625 | 233.0625 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 233.0625 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM15 | PPM | 15.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 20 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM15 | PPM | 15.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 20 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM15 | PPM | 15.2.25 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.26 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM15 | PPM | 15.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 20 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 21 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM16 | PPM | 16.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 21 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM16 | PPM | 16.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 21 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM16 | PPM | 16.1.24 | Main Switchgear | LV Disconnect | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 1.5 | 0 | 1.5 | COMPLETED | READY |  | 21 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 225 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 233.0625 | 233.0625 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 233.0625 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM16 | PPM | 16.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 21 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM16 | PPM | 16.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 21 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM16 | PPM | 16.2.25 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.26 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM16 | PPM | 16.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 21 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 22 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM17 | PPM | 17.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 22 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM17 | PPM | 17.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 22 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM17 | PPM | 17.1.24 | Main Switchgear | LV Disconnect | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 1.5 | 0 | 1.5 | COMPLETED | READY |  | 22 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 225 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 233.0625 | 233.0625 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 233.0625 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM17 | PPM | 17.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 22 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM17 | PPM | 17.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 22 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM17 | PPM | 17.2.25 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.26 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM17 | PPM | 17.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 22 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 23 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM18 | PPM | 18.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 23 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM18 | PPM | 18.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 23 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM18 | PPM | 18.1.24 | Main Switchgear | LV Disconnect | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 1.5 | 0 | 1.5 | COMPLETED | READY |  | 23 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 225 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 233.0625 | 233.0625 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 233.0625 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM18 | PPM | 18.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 23 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM18 | PPM | 18.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 23 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM18 | PPM | 18.2.25 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.26 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM18 | PPM | 18.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 23 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 24 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM19 | PPM | 19.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 24 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM19 | PPM | 19.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 24 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM19 | PPM | 19.1.24 | Main Switchgear | LV Disconnect | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 1.5 | 0 | 1.5 | COMPLETED | READY |  | 24 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 225 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 233.0625 | 233.0625 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 233.0625 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM19 | PPM | 19.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 24 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM19 | PPM | 19.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 24 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM19 | PPM | 19.2.25 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.26 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM19 | PPM | 19.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 24 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 25 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM20 | PPM | 20.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 25 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM20 | PPM | 20.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 25 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM20 | PPM | 20.1.24 | Main Switchgear | LV Disconnect | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 1.5 | 0 | 1.5 | COMPLETED | READY |  | 25 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 225 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 233.0625 | 233.0625 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 233.0625 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM20 | PPM | 20.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 25 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM20 | PPM | 20.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 25 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM20 | PPM | 20.2.25 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.26 | PDU | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM20 | PPM | 20.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 25 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  | NOT AVAILABLE |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 26 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM21 | PPM | 21.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 26 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM21 | PPM | 21.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 26 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM21 | PPM | 21.1.24 | Main Switchgear | LV Disconnect |  |  |  | A phase fuse failed resistance test | MINOR DEFICIENCY | TRUE | 2025-11-04 | A phase fuse failed resistance test | 100% |  | 1.5 | 0 | 1.5 | COMPLETED | READY |  | 26 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 225 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 233.0625 | 233.0625 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 233.0625 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM21 | PPM | 21.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 26 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM21 | PPM | 21.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 26 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM21 | PPM | 21.2.25 | PDU | Switchboard | [5 empty] | TRUE |  |  | 0% |  | 4 | 4 | 4 | NOT STARTED | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 | NOT STARTED - | NOT STARTED - READY |  | Not Started ¦ NOT STARTED ¦
LAS16.PPM21 | PPM | 21.2.26 | PDU | Switchboard | [5 empty] | TRUE |  |  | 0% |  | 4 | 4 | 4 | NOT STARTED | READY |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 | NOT STARTED - | NOT STARTED - READY |  | Not Started ¦ NOT STARTED ¦
LAS16.PPM21 | PPM | 21.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  | ON HOLD |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  | ON HOLD |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM21 | PPM | 21.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 26 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  | NOT AVAILABLE |  | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM22 | PPM | 22.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.1.24 | Main Switchgear | LV Disconnect | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 1.5 | 0 | 1.5 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 225 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 233.0625 | 233.0625 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 233.0625 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.25 | PDU | Switchboard | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.26 | PDU | Switchboard | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 27 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM22 | PPM | 22.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  | ON HOLD | LOW | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  | LOW - ON HOLD | Not Started ¦ ¦ LOW
LAS16.PPM22 | PPM | 22.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  | ON HOLD | LOW | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  | LOW - ON HOLD | Not Started ¦ ¦ LOW
LAS16.PPM22 | PPM | 22.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  | NOT AVAILABLE | LOW | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  | LOW - NOT AVAILABLE | Not Started ¦ ¦ LOW
LAS16.PPM22 | PPM | 22.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  | NOT AVAILABLE | LOW | 27 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  | LOW - NOT AVAILABLE | Not Started ¦ ¦ LOW
LAS16.PPM23 | PPM | 23.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM23 | PPM | 23.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM23 | PPM | 23.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM23 | PPM | 23.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM23 | PPM | 23.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM23 | PPM | 23.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM23 | PPM | 23.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM23 | PPM | 23.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM23 | PPM | 23.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM23 | PPM | 23.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM23 | PPM | 23.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM23 | PPM | 23.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM23 | PPM | 23.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM23 | PPM | 23.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM23 | PPM | 23.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM23 | PPM | 23.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM23 | PPM | 23.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM23 | PPM | 23.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM23 | PPM | 23.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM23 | PPM | 23.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 18.6 | 18.6 | 18.6 |  | NOT AVAILABLE |  | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7998 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM23 | PPM | 23.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.1.24 | Main Switchgear | LV Disconnect | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 1.5 | 0 | 1.5 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 225 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 233.0625 | 233.0625 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 233.0625 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.25 | PDU | Switchboard | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.26 | PDU | Switchboard | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 28 | 150 | 24331.725 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM23 | PPM | 23.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  | ON HOLD | LOW | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  | LOW - ON HOLD | Not Started ¦ ¦ LOW
LAS16.PPM23 | PPM | 23.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  | ON HOLD | LOW | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  | LOW - ON HOLD | Not Started ¦ ¦ LOW
LAS16.PPM23 | PPM | 23.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  | NOT AVAILABLE | LOW | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  | LOW - NOT AVAILABLE | Not Started ¦ ¦ LOW
LAS16.PPM23 | PPM | 23.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  | NOT AVAILABLE | LOW | 28 | 150 | 24331.725 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  | LOW - NOT AVAILABLE | Not Started ¦ ¦ LOW
LAS16.PPM24 | PPM | 24.1.1 | Main Switchgear | Switchboard | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM24 | PPM | 24.1.2 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM24 | PPM | 24.1.3 | Main Switchgear | Circuit Breakers -Primary | 5000AF / 4200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM24 | PPM | 24.1.4 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM24 | PPM | 24.1.5 | Main Switchgear | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM24 | PPM | 24.1.6 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM24 | PPM | 24.1.7 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM24 | PPM | 24.1.8 | Main Switchgear | Circuit Breakers -Primary | 600AF / 400 AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM24 | PPM | 24.1.9 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM24 | PPM | 24.1.10 | Main Switchgear | Circuit Breakers -Primary | 1200AF / 800AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM24 | PPM | 24.1.11 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM24 | PPM | 24.1.12 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM24 | PPM | 24.1.13 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM24 | PPM | 24.1.14 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM24 | PPM | 24.1.15 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM24 | PPM | 24.1.16 | Main Switchgear | Circuit Breakers -Primary | 2000AF / 1600AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM24 | PPM | 24.1.17 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM24 | PPM | 24.1.18 | Main Switchgear | Circuit Breakers -Primary | 3000AT / 2500AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM24 | PPM | 24.1.19 | Main Switchgear | Circuit Breakers -Primary | HLP02A MAIN |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  | READY |  | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.129 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM24 | PPM | 24.1.20 | Main Switchgear | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 19.8 | 19.8 | 19.8 |  | NOT AVAILABLE |  | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.8514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8514 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.PPM24 | PPM | 24.1.21 | Main Switchgear | Panelboards | HLP01A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.1.22 | Main Switchgear | Panelboards | HLP02A |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0215 | 2.6875 | 0 | 77.6875 | 77.6875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 77.6875 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.1.23 | Main Switchgear | XFMR - Dry-Type, Small | TLVP |  |  |  |  | TRUE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.1.24 | Main Switchgear | LV Disconnect | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 1.5 | 0 | 1.5 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 225 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 8.0625 | 0 | 233.0625 | 233.0625 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 233.0625 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.1 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.2 | PDU | Circuit Breakers -Secondary | 1600AF / 1600AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.3 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.4 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.5 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.6 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.7 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.8 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.9 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.10 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.11 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.12 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.13 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.14 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.15 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.16 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.17 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.18 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.19 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.20 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.21 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.22 | PDU | Circuit Breakers -Secondary | 400AF / 400AT |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 10.75 | 0 | 310.75 | 310.75 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 310.75 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.23 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.24 | PDU | XFMR - Dry-Type, Large | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.25 | PDU | Switchboard | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.26 | PDU | Switchboard | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 29 | 150 | 24518.175 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.172 | 21.5 | 0 | 621.5 | 621.5 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 621.5 | 2025-11-09 | Nov-2025 | 155.375 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.PPM24 | PPM | 24.2.27 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  | ON HOLD | LOW | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  | LOW - ON HOLD | Not Started ¦ ¦ LOW
LAS16.PPM24 | PPM | 24.2.28 | PDU | PDU Load Bank | [5 empty] | FALSE |  |  | 0% |  | 5 | 5 | 5 |  | ON HOLD | LOW | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  | LOW - ON HOLD | Not Started ¦ ¦ LOW
LAS16.PPM24 | PPM | 24.3.1 | Grounding | Point-to-Point | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  | NOT AVAILABLE | LOW | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0645 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  | LOW - NOT AVAILABLE | Not Started ¦ ¦ LOW
LAS16.PPM24 | PPM | 24.3.2 | Grounding | Ground Resistance - Clamp | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  | NOT AVAILABLE | LOW | 29 | 150 | 24518.175 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  | LOW - NOT AVAILABLE | Not Started ¦ ¦ LOW
LAS16.GDB01-12 | GDB | 25.1.1 | GDB01 | Switchboard | GDB SWBD |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.1.2 | GDB01 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.1.3 | GDB01 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.1.4 | GDB01 | XFMR - Dry-Type, Small | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.1.5 | GDB01 | Panelboards | [5 empty] | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.1.6 | GDB01 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.1.7 | GDB01 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.1.8 | GDB01 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.2.1 | GDB02 | Switchboard | GDB SWBD |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.2.2 | GDB02 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.2.3 | GDB02 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.2.4 | GDB02 | XFMR - Dry-Type, Small | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.2.5 | GDB02 | Panelboards | [5 empty] | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.2.6 | GDB02 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.2.7 | GDB02 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.2.8 | GDB02 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.3.1 | GDB03 | Switchboard | GDB SWBD |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.3.2 | GDB03 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.3.3 | GDB03 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.3.4 | GDB03 | XFMR - Dry-Type, Small | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.3.5 | GDB03 | Panelboards | [5 empty] | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.3.6 | GDB03 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.3.7 | GDB03 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.3.8 | GDB03 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.4.1 | GDB04 | Switchboard | GDB SWBD |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.4.2 | GDB04 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.4.3 | GDB04 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.4.4 | GDB04 | XFMR - Dry-Type, Small | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.4.5 | GDB04 | Panelboards | [5 empty] | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.4.6 | GDB04 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.4.7 | GDB04 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.4.8 | GDB04 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.5.1 | GDB05 | Switchboard | GDB SWBD |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.5.2 | GDB05 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.5.3 | GDB05 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.5.4 | GDB05 | XFMR - Dry-Type, Small | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.5.5 | GDB05 | Panelboards | [5 empty] | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.5.6 | GDB05 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.5.7 | GDB05 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.5.8 | GDB05 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.6.1 | GDB06 | Switchboard | GDB SWBD |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.6.2 | GDB06 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.6.3 | GDB06 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.6.4 | GDB06 | XFMR - Dry-Type, Small | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.6.5 | GDB06 | Panelboards | [5 empty] | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.6.6 | GDB06 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.6.7 | GDB06 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.6.8 | GDB06 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.7.1 | GDB07 | Switchboard | GDB SWBD |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.7.2 | GDB07 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.7.3 | GDB07 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.7.4 | GDB07 | XFMR - Dry-Type, Small | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.7.5 | GDB07 | Panelboards | [5 empty] | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.7.6 | GDB07 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.7.7 | GDB07 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.7.8 | GDB07 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.8.1 | GDB08 | Switchboard | GDB SWBD |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.8.2 | GDB08 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.8.3 | GDB08 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.8.4 | GDB08 | XFMR - Dry-Type, Small | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.8.5 | GDB08 | Panelboards | [5 empty] | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.8.6 | GDB08 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.8.7 | GDB08 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.8.8 | GDB08 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.9.1 | GDB09 | Switchboard | GDB SWBD |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.9.2 | GDB09 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.9.3 | GDB09 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.9.4 | GDB09 | XFMR - Dry-Type, Small | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.9.5 | GDB09 | Panelboards | [5 empty] | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.9.6 | GDB09 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.9.7 | GDB09 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.9.8 | GDB09 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.10.1 | GDB10 | Switchboard | GDB SWBD |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.10.2 | GDB10 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.10.3 | GDB10 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.10.4 | GDB10 | XFMR - Dry-Type, Small | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.10.5 | GDB10 | Panelboards | [5 empty] | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.10.6 | GDB10 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.10.7 | GDB10 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.10.8 | GDB10 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.11.1 | GDB11 | Switchboard | GDB SWBD |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.11.2 | GDB11 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.11.3 | GDB11 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.11.4 | GDB11 | XFMR - Dry-Type, Small | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.11.5 | GDB11 | Panelboards | [5 empty] | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.11.6 | GDB11 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.11.7 | GDB11 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.11.8 | GDB11 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.12.1 | GDB12 | Switchboard | GDB SWBD |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.12.2 | GDB12 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.12.3 | GDB12 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.12.4 | GDB12 | XFMR - Dry-Type, Small | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.12.5 | GDB12 | Panelboards | [5 empty] | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.12.6 | GDB12 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.12.7 | GDB12 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB01-12 | GDB | 25.12.8 | GDB12 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  |  |  | 30 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.1.1 | GDB13 | Switchboard | GDB SWBD |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 612.6 | 612.6 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 612.6 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.1.2 | GDB13 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.1.3 | GDB13 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.1.4 | GDB13 | XFMR - Dry-Type, Small | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 306.3 | 306.3 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 306.3 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.1.5 | GDB13 | Panelboards | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 76.575 | 76.575 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 76.575 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.1.6 | GDB13 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.1.7 | GDB13 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.1.8 | GDB13 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.2.1 | GDB14 | Switchboard | GDB SWBD |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 612.6 | 612.6 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 612.6 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.2.2 | GDB14 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.2.3 | GDB14 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.2.4 | GDB14 | XFMR - Dry-Type, Small | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 306.3 | 306.3 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 306.3 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.2.5 | GDB14 | Panelboards | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 76.575 | 76.575 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 76.575 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.2.6 | GDB14 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.2.7 | GDB14 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.2.8 | GDB14 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.3.1 | GDB15 | Switchboard | GDB SWBD |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 612.6 | 612.6 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 612.6 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.3.2 | GDB15 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.3.3 | GDB15 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.3.4 | GDB15 | XFMR - Dry-Type, Small | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 306.3 | 306.3 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 306.3 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.3.5 | GDB15 | Panelboards | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 76.575 | 76.575 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 76.575 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.3.6 | GDB15 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.3.7 | GDB15 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.3.8 | GDB15 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.4.1 | GDB16 | Switchboard | GDB SWBD |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 612.6 | 612.6 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 612.6 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.4.2 | GDB16 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.4.3 | GDB16 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.4.4 | GDB16 | XFMR - Dry-Type, Small | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 306.3 | 306.3 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 306.3 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.4.5 | GDB16 | Panelboards | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 76.575 | 76.575 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 76.575 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.4.6 | GDB16 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.4.7 | GDB16 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.4.8 | GDB16 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.5.1 | GDB17 | Switchboard | GDB SWBD |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 612.6 | 612.6 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 612.6 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.5.2 | GDB17 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.5.3 | GDB17 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.5.4 | GDB17 | XFMR - Dry-Type, Small | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 306.3 | 306.3 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 306.3 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.5.5 | GDB17 | Panelboards | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 76.575 | 76.575 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 76.575 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.5.6 | GDB17 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.5.7 | GDB17 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.5.8 | GDB17 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.6.1 | GDB18 | Switchboard | GDB SWBD |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 612.6 | 612.6 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 612.6 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.6.2 | GDB18 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.6.3 | GDB18 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.6.4 | GDB18 | XFMR - Dry-Type, Small | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 306.3 | 306.3 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 306.3 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.6.5 | GDB18 | Panelboards | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 76.575 | 76.575 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 76.575 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.6.6 | GDB18 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.6.7 | GDB18 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.6.8 | GDB18 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.7.1 | GDB19 | Switchboard | GDB SWBD |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 612.6 | 612.6 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 612.6 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.7.2 | GDB19 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.7.3 | GDB19 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.7.4 | GDB19 | XFMR - Dry-Type, Small |  |  |  | Vector Pattern incorrect from Factory. | NON-SERVICEABLE | FALSE |  | Vector Pattern incorrect from Factory. | 0% |  | 2 | 2 | 2 | NOT STARTED | ON HOLD | HIGH | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 | NOT STARTED - HIGH | NOT STARTED - ON HOLD | HIGH - ON HOLD | Not Started ¦ NOT STARTED ¦ HIGH
LAS16.GDB13-24 | GDB | 26.7.5 | GDB19 | Panelboards | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 76.575 | 76.575 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 76.575 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.7.6 | GDB19 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.7.7 | GDB19 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.7.8 | GDB19 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.8.1 | GDB20 | Switchboard | GDB SWBD |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 612.6 | 612.6 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 612.6 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.8.2 | GDB20 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.8.3 | GDB20 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.8.4 | GDB20 | XFMR - Dry-Type, Small | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 306.3 | 306.3 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 306.3 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.8.5 | GDB20 | Panelboards | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 76.575 | 76.575 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 76.575 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.8.6 | GDB20 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.8.7 | GDB20 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.8.8 | GDB20 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.9.1 | GDB21 | Switchboard | GDB SWBD |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 612.6 | 612.6 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 612.6 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.9.2 | GDB21 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.9.3 | GDB21 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.9.4 | GDB21 | XFMR - Dry-Type, Small | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 306.3 | 306.3 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 306.3 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.9.5 | GDB21 | Panelboards | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 76.575 | 76.575 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 76.575 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.9.6 | GDB21 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.9.7 | GDB21 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.9.8 | GDB21 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.10.1 | GDB22 | Switchboard | GDB SWBD |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 612.6 | 612.6 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 612.6 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.10.2 | GDB22 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.10.3 | GDB22 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.10.4 | GDB22 | XFMR - Dry-Type, Small | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 306.3 | 306.3 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 306.3 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.10.5 | GDB22 | Panelboards | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 76.575 | 76.575 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 76.575 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.10.6 | GDB22 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.10.7 | GDB22 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.10.8 | GDB22 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.11.1 | GDB23 | Switchboard | GDB SWBD |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 612.6 | 612.6 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 612.6 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.11.2 | GDB23 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 | NOT STARTED | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 | NOT STARTED - | NOT STARTED - READY |  | Not Started ¦ NOT STARTED ¦
LAS16.GDB13-24 | GDB | 26.11.3 | GDB23 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 | NOT STARTED | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 | NOT STARTED - | NOT STARTED - READY |  | Not Started ¦ NOT STARTED ¦
LAS16.GDB13-24 | GDB | 26.11.4 | GDB23 | XFMR - Dry-Type, Small | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 306.3 | 306.3 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 306.3 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.11.5 | GDB23 | Panelboards | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 76.575 | 76.575 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 76.575 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.11.6 | GDB23 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.11.7 | GDB23 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.11.8 | GDB23 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.12.1 | GDB24 | Switchboard | GDB SWBD |  |  |  |  | FALSE | 2025-11-04 |  | 100% |  | 4 | 0 | 4 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 600 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 12.6 | 0 | 612.6 | 612.6 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 612.6 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.12.2 | GDB24 | Circuit Breakers -Primary | GDB MAIN |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 | NOT STARTED | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 | NOT STARTED - | NOT STARTED - READY |  | Not Started ¦ NOT STARTED ¦
LAS16.GDB13-24 | GDB | 26.12.3 | GDB24 | Circuit Breakers -Primary | GDB LB |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 | NOT STARTED | READY |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 | NOT STARTED - | NOT STARTED - READY |  | Not Started ¦ NOT STARTED ¦
LAS16.GDB13-24 | GDB | 26.12.4 | GDB24 | XFMR - Dry-Type, Small | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 2 | 0 | 2 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 300 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 6.3 | 0 | 306.3 | 306.3 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 306.3 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.12.5 | GDB24 | Panelboards | [5 empty] | FALSE | 2025-11-04 |  | 100% |  | 0.5 | 0 | 0.5 | COMPLETED | READY |  | 31 | 150 | 36388.44 | 1 | 1 | 2025-11-09 | Nov-2025 | 75 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0105 | 1.575 | 0 | 76.575 | 76.575 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 76.575 | 2025-11-09 | Nov-2025 | 153.15 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
LAS16.GDB13-24 | GDB | 26.12.6 | GDB24 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.3 | 0.3 | 0.3 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0063 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.12.7 | GDB24 | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.GDB13-24 | GDB | 26.12.8 | GDB24 | Ground Resistance - 2pt | [5 empty] | FALSE |  |  | 0% |  | 1 | 1 | 1 |  | NOT AVAILABLE |  | 31 | 150 | 36388.44 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.1.1 | GEN-H | Circuit Breakers -Primary | 1200AT / 1200AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.111 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.1.2 | GEN-H | Panelboards | LGH1 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.1.3 | GEN-H | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 1.2 | 1.2 | 1.2 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0444 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.1.4 | GEN-H | GROUND RESISTANCE | [5 empty] | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.148 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.2.1 | SES-H | Switchboard | SES-H |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.148 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.2.2 | SES-H | Circuit Breakers -Primary | 1200AT / 1200AT |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.148 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.2.3 | SES-H | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 1.2 | 1.2 | 1.2 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0444 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.3.1 | DB-H | Panelboards | DB-H |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.3.2 | DB-H | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 2.7 | 2.7 | 2.7 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0999 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.3.3 | DB-H | Circuit Breakers -Primary | HP1 |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.111 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.3.4 | DB-H | Circuit Breakers -Primary | HP2 |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.111 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.3.5 | DB-H | Panelboards | HP1 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.4.1 | HP1 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0555 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.4.2 | HP1 | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.111 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.4.3 | HP1 | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.111 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.4.4 | HP1 | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.111 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.5.1 | HP2 | Panelboards | HP2 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.5.2 | HP2 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 1.5 | 1.5 | 1.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0555 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.5.3 | HP2 | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.111 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.5.4 | HP2 | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.111 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.5.5 | HP2 | Circuit Breakers -Primary | 400AF / 400AT |  |  |  |  | FALSE |  |  | 0% |  | 3 | 3 | 3 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.111 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.6.1 | HUPS1 | XFMR - Dry-Type, Small | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.6.2 | HUPS1 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.9 | 0.9 | 0.9 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0333 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.6.3 | HUPS1 | Panelboards | U1A1 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.6.4 | HUPS1 | Panelboards | U1A2 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.7.1 | HUPS2 | XFMR - Dry-Type, Small | [5 empty] | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.7.2 | HUPS2 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 0.9 | 0.9 | 0.9 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0333 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.7.3 | HUPS2 | Panelboards | U2A1 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.7.4 | HUPS2 | Panelboards | U2A2 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.8.1 | HPP1.1 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 1.2 | 1.2 | 1.2 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0444 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.8.2 | HPP1.1 | XFMR - Dry-Type, Small | TLPP1.1 |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.8.3 | HPP1.1 | XFMR - Dry-Type, Small | TLPP1.1A |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.8.4 | HPP1.1 | Panelboards | HPP1.1 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.8.5 | HPP1.1 | Panelboards | LPP1.1 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.8.6 | HPP1.1 | Panelboards | LPP1.1A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.9.1 | HPP2.1 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 1.2 | 1.2 | 1.2 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0444 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.9.2 | HPP2.1 | XFMR - Dry-Type, Small | TLPP2.1 |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.9.3 | HPP2.1 | XFMR - Dry-Type, Small | TLPP2.1A |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.9.4 | HPP2.1 | Panelboards | HPP2.1 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.9.5 | HPP2.1 | Panelboards | LPP2.1 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.9.6 | HPP2.1 | Panelboards | LPP2.1A |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.10.1 | HPC1.1 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 1.8 | 1.8 | 1.8 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0666 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.10.2 | HPC1.1 | XFMR - Dry-Type, Small | TLPC1 |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.10.3 | HPC1.1 | Panelboards | HPC1.1 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.10.4 | HPC1.1 | Panelboards | LPC1.1 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.10.5 | HPC1.1 | Panelboards | LPC1.2 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.11.1 | HPC2.1 | LV Cables | [5 empty] | FALSE |  |  | 0% |  | 1.8 | 1.8 | 1.8 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0666 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.11.2 | HPC2.1 | XFMR - Dry-Type, Small | TLPC2 |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.11.3 | HPC2.1 | Panelboards | HPC2.1 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.11.4 | HPC2.1 | Panelboards | LPC2.1 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.11.5 | HPC2.1 | Panelboards | LPC2.2 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.12.1 | H1 | Panelboards | H1 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.12.2 | H1 | Panelboards | L1 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.12.3 | H1 | Panelboards | LT1 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.12.4 | H1 | Panelboards | LCC-P1 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.12.5 | H1 | XFMR - Dry-Type, Small | TH1 |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.12.6 | H1 | XFMR - Dry-Type, Small | TL1 |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.13.1 | H2 | Panelboards | H2 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.13.2 | H2 | Panelboards | L2 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.13.3 | H2 | Panelboards | LT2 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.13.4 | H2 | Panelboards | LCC-P2 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.13.5 | H2 | XFMR - Dry-Type, Small | TH2 |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.13.6 | H2 | XFMR - Dry-Type, Small | TL2 |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.14.1 | U1B1 | Panelboards | U1B1 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.14.2 | U1B1 | Panelboards | U1B2 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.14.3 | U1B1 | XFMR - Dry-Type, Small | TU1B |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.14.4 | U1B1 | Panelboards | U2B1 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.14.5 | U1B1 | Panelboards | U2B2 |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.14.6 | U1B1 | XFMR - Dry-Type, Small | TU2B |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.15.1 | LPP3.EV | Panelboards | LPP3.EV |  |  |  |  | FALSE |  |  | 0% |  | 0.5 | 0.5 | 0.5 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0185 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.15.2 | LPP3.EV | XFMR - Dry-Type, Small | TLPP3.EV |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.16.1 | ATS | ATS | DQ-1 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.148 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.16.2 | ATS | ATS | DQ-1 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.148 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
LAS16.HOUSE | HOUSE | 27.16.3 | ATS | ATS | ATS-H |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 32 | 150 | 17639.37 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.148 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.1 | MV Cables | LV Cables | SUB03A-MVS01R |  |  |  |  | FALSE |  |  | 0% |  | 8 | 8 | 8 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.2 | MV Cables | LV Cables | SUB03A-MVS02 |  |  |  |  | FALSE |  |  | 0% |  | 8 | 8 | 8 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.3 | MV Cables | LV Cables | SUB03A-MVS04 |  |  |  |  | FALSE |  |  | 0% |  | 8 | 8 | 8 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.4 | MV Cables | LV Cables | SUB03A-MVS06 |  |  |  |  | FALSE |  |  | 0% |  | 8 | 8 | 8 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.5 | MV Cables | LV Cables | SUB03B-MVS01 |  |  |  |  | FALSE |  |  | 0% |  | 8 | 8 | 8 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.6 | MV Cables | LV Cables | SUB03B-MVS03 |  |  |  |  | FALSE |  |  | 0% |  | 8 | 8 | 8 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.7 | MV Cables | LV Cables | SUB03B-MVS02R |  |  |  |  | FALSE |  |  | 0% |  | 8 | 8 | 8 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.8 | MV Cables | LV Cables | SUB03B-MVS05 |  |  |  |  | FALSE |  |  | 0% |  | 8 | 8 | 8 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.9 | MV Cables | MV Cables | MVS01-MVTH1 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.10 | MV Cables | MV Cables | MVS01-MVT01 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.11 | MV Cables | MV Cables | MVT01-MVT02 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.12 | MV Cables | MV Cables | MVT02-MVT03 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.13 | MV Cables | MV Cables | MVT03-MVT04 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.14 | MV Cables | MV Cables | MVS01R-PMS01R |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.15 | MV Cables | MV Cables | PMS01R-MVT04 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.16 | MV Cables | MV Cables | PMS01R-PMS0T1R |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.17 | MV Cables | MV Cables | PMS01R-MVT05 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.18 | MV Cables | MV Cables | MVT05-MVT06 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.19 | MV Cables | MV Cables | MVT06-MVT07 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.20 | MV Cables | MV Cables | MVT07-MVT08 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.21 | MV Cables | MV Cables | MVS02-MVT08 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.22 | MV Cables | MV Cables | MVS03-MVT12 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.23 | MV Cables | MV Cables | PMS0T1R-MVT09 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.24 | MV Cables | MV Cables | MVT09-MVT10 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.25 | MV Cables | MV Cables | MVT10-MVT11 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.26 | MV Cables | MV Cables | MVT11-MVT12 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.27 | MV Cables | MV Cables | PMS0T1R-PMS02R |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.28 | MV Cables | MV Cables | PMS0T1R-MVT13 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.29 | MV Cables | MV Cables | MVT13-MVT14 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.30 | MV Cables | MV Cables | MVT14-MVT15 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.31 | MV Cables | MV Cables | MVT15-MVT16 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.32 | MV Cables | MV Cables | MVS04-MVT16 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.33 | MV Cables | MV Cables | MVS05-MVT20 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.34 | MV Cables | MV Cables | MVS02R-PMS02R |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.35 | MV Cables | MV Cables | PMS02R-MVT17 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.36 | MV Cables | MV Cables | MVT17-MVT18 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.37 | MV Cables | MV Cables | MVT18-MVT19 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.38 | MV Cables | MV Cables | MVT19-MVT20 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.39 | MV Cables | MV Cables | PMS02R-MVT21 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.40 | MV Cables | MV Cables | MVT21-MVT22 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.41 | MV Cables | MV Cables | MVT22-MVT23 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.42 | MV Cables | MV Cables | MVT23-MVT24 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.1.43 | MV Cables | MV Cables | MVT24-MVS06 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.2.1 | MV Switches | MV Fused Swicth | MVS01R |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.06 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.2.2 | MV Switches | MV Fused Swicth | MVS02 |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.06 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.2.3 | MV Switches | MV Fused Swicth | MVS02R |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.06 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.2.4 | MV Switches | MV Fused Swicth | MVS03 |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.06 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.2.5 | MV Switches | MV Fused Swicth | MVS05 |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.06 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.2.6 | MV Switches | MV Fused Swicth | MVS06 |  |  |  |  | FALSE |  |  | 0% |  | 2 | 2 | 2 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.06 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.3.1 | Padmount Vista | Padmount Vista Switch | PMS01R |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.3.2 | Padmount Vista | Padmount Vista Switch | PMS0T1R |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.3.3 | Padmount Vista | Padmount Vista Switch | PMS02R |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.3.4 | Padmount Vista | Padmount Vista Switch | MVS01 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.3.5 | Padmount Vista | Padmount Vista Switch | MVS04 |  |  |  |  | FALSE |  |  | 0% |  | 4 | 4 | 4 |  |  |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.4.1 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVTH1 |  |  |  |  | FALSE |  |  | 0% |  | 12 | 12 | 12 | NOT STARTED | NOT AVAILABLE |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 | NOT STARTED - | NOT STARTED - NOT AVAILABLE |  | Not Started ¦ NOT STARTED ¦
MV | MV | 28.4.2 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT01 |  |  |  | ACCEPTABLE | TRUE | 2025-11-04 |  | 100% |  | 12 | 0 | 12 | COMPLETED | READY |  | 33 | 150 | 90312 | 1 | 1 | 2025-11-09 | Nov-2025 | 1800 | 0 | 0 | 0 | 0 | 0.36 | 54 | 0 | 0 | 0 | 0 | 0 | 167.9104 | 0.36 | 54 | 167.9104 | 2021.9104 | 2021.9104 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 2021.9104 | 2025-11-09 | Nov-2025 | 168.4925 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
MV | MV | 28.4.3 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT02 |  |  |  | ACCEPTABLE | TRUE | 2025-11-04 |  | 100% |  | 12 | 0 | 12 | COMPLETED | READY |  | 33 | 150 | 90312 | 1 | 1 | 2025-11-09 | Nov-2025 | 1800 | 0 | 0 | 0 | 0 | 0.36 | 54 | 0 | 0 | 0 | 0 | 0 | 167.9104 | 0.36 | 54 | 167.9104 | 2021.9104 | 2021.9104 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 2021.9104 | 2025-11-09 | Nov-2025 | 168.4925 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
MV | MV | 28.4.4 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT03 |  |  |  | ACCEPTABLE | TRUE | 2025-11-04 |  | 100% |  | 12 | 0 | 12 | COMPLETED | READY |  | 33 | 150 | 90312 | 1 | 1 | 2025-11-09 | Nov-2025 | 1800 | 0 | 0 | 0 | 0 | 0.36 | 54 | 0 | 0 | 0 | 0 | 0 | 167.9104 | 0.36 | 54 | 167.9104 | 2021.9104 | 2021.9104 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 2021.9104 | 2025-11-09 | Nov-2025 | 168.4925 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
MV | MV | 28.4.5 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT04 |  |  |  | ACCEPTABLE | TRUE | 2025-11-04 |  | 100% |  | 12 | 0 | 12 | COMPLETED | READY |  | 33 | 150 | 90312 | 1 | 1 | 2025-11-09 | Nov-2025 | 1800 | 0 | 0 | 0 | 0 | 0.36 | 54 | 0 | 0 | 0 | 0 | 0 | 167.9104 | 0.36 | 54 | 167.9104 | 2021.9104 | 2021.9104 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 2021.9104 | 2025-11-09 | Nov-2025 | 168.4925 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
MV | MV | 28.4.6 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT05 |  |  |  | ACCEPTABLE | TRUE | 2025-11-04 |  | 100% |  | 12 | 0 | 12 | COMPLETED | READY |  | 33 | 150 | 90312 | 1 | 1 | 2025-11-09 | Nov-2025 | 1800 | 0 | 0 | 0 | 0 | 0.36 | 54 | 0 | 0 | 0 | 0 | 0 | 167.9104 | 0.36 | 54 | 167.9104 | 2021.9104 | 2021.9104 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 2021.9104 | 2025-11-09 | Nov-2025 | 168.4925 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
MV | MV | 28.4.7 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT06 |  |  |  | ACCEPTABLE | TRUE | 2025-11-04 |  | 100% |  | 12 | 0 | 12 | COMPLETED | READY |  | 33 | 150 | 90312 | 1 | 1 | 2025-11-09 | Nov-2025 | 1800 | 0 | 0 | 0 | 0 | 0.36 | 54 | 0 | 0 | 0 | 0 | 0 | 167.9104 | 0.36 | 54 | 167.9104 | 2021.9104 | 2021.9104 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 2021.9104 | 2025-11-09 | Nov-2025 | 168.4925 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
MV | MV | 28.4.8 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT07 |  |  |  | ACCEPTABLE | TRUE | 2025-11-04 |  | 100% |  | 12 | 0 | 12 | COMPLETED | READY |  | 33 | 150 | 90312 | 1 | 1 | 2025-11-09 | Nov-2025 | 1800 | 0 | 0 | 0 | 0 | 0.36 | 54 | 0 | 0 | 0 | 0 | 0 | 167.9104 | 0.36 | 54 | 167.9104 | 2021.9104 | 2021.9104 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 2021.9104 | 2025-11-09 | Nov-2025 | 168.4925 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
MV | MV | 28.4.9 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT08 |  |  |  | ACCEPTABLE | TRUE | 2025-11-04 |  | 100% |  | 12 | 0 | 12 | COMPLETED | READY |  | 33 | 150 | 90312 | 1 | 1 | 2025-11-09 | Nov-2025 | 1800 | 0 | 0 | 0 | 0 | 0.36 | 54 | 0 | 0 | 0 | 0 | 0 | 167.9104 | 0.36 | 54 | 167.9104 | 2021.9104 | 2021.9104 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 2021.9104 | 2025-11-09 | Nov-2025 | 168.4925 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
MV | MV | 28.4.10 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT09 |  |  |  | ACCEPTABLE | TRUE | 2025-11-04 |  | 100% |  | 12 | 0 | 12 | COMPLETED | READY |  | 33 | 150 | 90312 | 1 | 1 | 2025-11-09 | Nov-2025 | 1800 | 0 | 0 | 0 | 0 | 0.36 | 54 | 0 | 0 | 0 | 0 | 0 | 167.9104 | 0.36 | 54 | 167.9104 | 2021.9104 | 2021.9104 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 2021.9104 | 2025-11-09 | Nov-2025 | 168.4925 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
MV | MV | 28.4.11 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT10 |  |  |  | ACCEPTABLE | TRUE | 2025-11-04 |  | 100% |  | 12 | 0 | 12 | COMPLETED | READY |  | 33 | 150 | 90312 | 1 | 1 | 2025-11-09 | Nov-2025 | 1800 | 0 | 0 | 0 | 0 | 0.36 | 54 | 0 | 0 | 0 | 0 | 0 | 167.9104 | 0.36 | 54 | 167.9104 | 2021.9104 | 2021.9104 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 2021.9104 | 2025-11-09 | Nov-2025 | 168.4925 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
MV | MV | 28.4.12 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT11 |  |  |  | ACCEPTABLE | TRUE | 2025-11-04 |  | 100% |  | 12 | 0 | 12 | COMPLETED | READY |  | 33 | 150 | 90312 | 1 | 1 | 2025-11-09 | Nov-2025 | 1800 | 0 | 0 | 0 | 0 | 0.36 | 54 | 0 | 0 | 0 | 0 | 0 | 167.9104 | 0.36 | 54 | 167.9104 | 2021.9104 | 2021.9104 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 2021.9104 | 2025-11-09 | Nov-2025 | 168.4925 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
MV | MV | 28.4.13 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT12 |  |  |  | ACCEPTABLE | TRUE | 2025-11-04 |  | 100% |  | 12 | 0 | 12 | COMPLETED | READY |  | 33 | 150 | 90312 | 1 | 1 | 2025-11-09 | Nov-2025 | 1800 | 0 | 0 | 0 | 0 | 0.36 | 54 | 0 | 0 | 0 | 0 | 0 | 167.9104 | 0.36 | 54 | 167.9104 | 2021.9104 | 2021.9104 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 2021.9104 | 2025-11-09 | Nov-2025 | 168.4925 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
MV | MV | 28.4.14 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT13 |  |  |  | ACCEPTABLE | TRUE | 2025-11-04 |  | 100% |  | 12 | 0 | 12 | COMPLETED | READY |  | 33 | 150 | 90312 | 1 | 1 | 2025-11-09 | Nov-2025 | 1800 | 0 | 0 | 0 | 0 | 0.36 | 54 | 0 | 0 | 0 | 0 | 0 | 167.9104 | 0.36 | 54 | 167.9104 | 2021.9104 | 2021.9104 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 2021.9104 | 2025-11-09 | Nov-2025 | 168.4925 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
MV | MV | 28.4.15 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT14 |  |  |  | ACCEPTABLE | TRUE | 2025-11-04 |  | 100% |  | 12 | 0 | 12 | COMPLETED | READY |  | 33 | 150 | 90312 | 1 | 1 | 2025-11-09 | Nov-2025 | 1800 | 0 | 0 | 0 | 0 | 0.36 | 54 | 0 | 0 | 0 | 0 | 0 | 167.9104 | 0.36 | 54 | 167.9104 | 2021.9104 | 2021.9104 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 2021.9104 | 2025-11-09 | Nov-2025 | 168.4925 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
MV | MV | 28.4.16 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT15 |  |  |  | ACCEPTABLE | TRUE | 2025-11-04 |  | 100% |  | 12 | 0 | 12 | COMPLETED | READY |  | 33 | 150 | 90312 | 1 | 1 | 2025-11-09 | Nov-2025 | 1800 | 0 | 0 | 0 | 0 | 0.36 | 54 | 0 | 0 | 0 | 0 | 0 | 167.9104 | 0.36 | 54 | 167.9104 | 2021.9104 | 2021.9104 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 2021.9104 | 2025-11-09 | Nov-2025 | 168.4925 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
MV | MV | 28.4.17 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT16 |  |  |  | ACCEPTABLE | TRUE | 2025-11-04 |  | 100% |  | 12 | 0 | 12 | COMPLETED | READY |  | 33 | 150 | 90312 | 1 | 1 | 2025-11-09 | Nov-2025 | 1800 | 0 | 0 | 0 | 0 | 0.36 | 54 | 0 | 0 | 0 | 0 | 0 | 167.9104 | 0.36 | 54 | 167.9104 | 2021.9104 | 2021.9104 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 2021.9104 | 2025-11-09 | Nov-2025 | 168.4925 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
MV | MV | 28.4.18 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT17 |  |  | Completed besides Oil Sample Bill 11/12 for Sept | ACCEPTABLE | TRUE |  | Completed besides Oil Sample Bill 11/12 for Sept | 0% |  | 12 | 12 | 12 |  | READY |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.4.19 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT18 |  |  | Completed besides Oil Sample Bill 11/12 for Sept | ACCEPTABLE | TRUE |  | Completed besides Oil Sample Bill 11/12 for Sept | 0% |  | 12 | 12 | 12 |  | READY |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.4.20 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT19 |  |  | Completed besides Oil Sample Bill 11/12 for Sept | ACCEPTABLE | TRUE |  | Completed besides Oil Sample Bill 11/12 for Sept | 0% |  | 12 | 12 | 12 |  | READY |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.4.21 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT20 |  |  | Completed besides Oil Sample Bill 11/12 for Sept | ACCEPTABLE | TRUE |  | Completed besides Oil Sample Bill 11/12 for Sept | 0% |  | 12 | 12 | 12 |  | READY |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.4.22 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT21 |  |  | Completed besides Oil Sample Bill 11/12 for Sept | ACCEPTABLE | TRUE |  | Completed besides Oil Sample Bill 11/12 for Sept | 0% |  | 12 | 12 | 12 |  | READY |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.4.23 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT22 |  |  | Completed besides Oil Sample Bill 11/12 for Sept | ACCEPTABLE | TRUE |  | Completed besides Oil Sample Bill 11/12 for Sept | 0% |  | 12 | 12 | 12 |  | READY |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.4.24 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT23 |  |  | Completed besides Oil Sample Bill 11/12 for Sept | ACCEPTABLE | TRUE |  | Completed besides Oil Sample Bill 11/12 for Sept | 0% |  | 12 | 12 | 12 |  | READY |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
MV | MV | 28.4.25 | Oil-Filled XFMR's | XFMR, Oil-Filled, Padmount | MVT24 |  |  | Completed besides Oil Sample Bill 11/12 for Sept | ACCEPTABLE | TRUE |  | Completed besides Oil Sample Bill 11/12 for Sept | 0% |  | 12 | 12 | 12 |  | READY |  | 33 | 150 | 90312 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (1-120) | RPP | 29.1.1 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.2 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.3 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.4 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.5 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.6 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.7 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.8 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.9 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.10 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.11 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.12 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.13 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.14 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.15 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.16 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.17 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.18 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.19 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.20 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.21 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.22 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.23 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.24 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.25 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.26 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.27 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.28 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.29 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.30 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.31 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.32 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.33 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.34 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.35 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.36 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.37 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.38 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.39 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.40 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.41 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.42 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.43 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.44 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.45 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.46 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.47 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.48 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.49 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.50 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.51 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.52 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.53 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.54 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.55 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.56 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.57 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.58 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.59 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.60 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.61 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.62 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.63 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.64 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.65 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.66 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.67 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.68 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.69 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.70 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.71 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.72 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.73 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.74 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.75 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.76 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.77 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.78 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.79 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.80 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.81 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.82 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.83 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.84 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.85 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.86 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.87 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.88 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.89 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.90 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.91 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.92 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.93 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.94 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.95 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.96 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.97 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.98 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.99 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.100 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.101 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.102 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.103 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.104 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.105 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.106 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.107 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.108 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.109 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.110 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.111 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.112 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.113 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.114 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.115 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.116 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.117 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.118 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.119 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (1-120) | RPP | 29.1.120 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 34 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.1 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED | READY |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.2 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED | READY |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.3 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED | READY |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.4 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED | READY |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.5 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED | READY |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.6 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED | READY |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.7 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED | READY |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.8 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED | READY |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.9 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED | READY |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.10 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED | READY |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.11 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED | READY |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.12 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED | READY |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - READY |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.13 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.14 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.15 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.16 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.17 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.18 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.19 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.20 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.21 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.22 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.23 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.24 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.25 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.26 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.27 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.28 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.29 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.30 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.31 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.32 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.33 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.34 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.35 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.36 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.37 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.38 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.39 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.40 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.41 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.42 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.43 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.44 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.45 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.46 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.47 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.48 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.49 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.50 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.51 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.52 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.53 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.54 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.55 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.56 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.57 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.58 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.59 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.60 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.61 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.62 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.63 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.64 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.65 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.66 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.67 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.68 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.69 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.70 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.71 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.72 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.73 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.74 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.75 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.76 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.77 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.78 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.79 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.80 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.81 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.82 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.83 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.84 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.85 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.86 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.87 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.88 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.89 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.90 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.91 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.92 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.93 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.94 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.95 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.96 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.97 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.98 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.99 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.100 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.101 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.102 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.103 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.104 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.105 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.106 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.107 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.108 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.109 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.110 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.111 | RPP's | RPP | [5 empty] | TRUE | 2025-11-04 |  | 100% |  | 2.5 | 0 | 2.5 | COMPLETED |  |  | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - | COMPLETED - |  | Completed ¦ COMPLETED ¦ | 12
RPP's (121-240) | RPP | 30.1.112 | RPP's | RPP |  |  |  | RPP 3716-5070 B Phase No Valid Contact Resistance | NON-SERVICEABLE | TRUE | 2025-11-04 | RPP 3716-5070 B Phase No Valid Contact Resistance | 100% |  | 2.5 | 0 | 2.5 | COMPLETED | ON HOLD | HIGH | 35 | 150 | 45225 | 1 | 1 | 2025-11-09 | Nov-2025 | 375 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 1.875 | 0 | 376.875 | 376.875 | Nov-2025 | Q4-2025 | 2025 | Last Week | This Month | This Quarter | 376.875 | 2025-11-09 | Nov-2025 | 150.75 | Completed | 1 | 1 | COMPLETED - HIGH | COMPLETED - ON HOLD | HIGH - ON HOLD | Completed ¦ COMPLETED ¦ HIGH | 12
RPP's (121-240) | RPP | 30.1.113 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 35 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (121-240) | RPP | 30.1.114 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 35 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (121-240) | RPP | 30.1.115 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 35 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (121-240) | RPP | 30.1.116 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 35 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (121-240) | RPP | 30.1.117 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 35 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (121-240) | RPP | 30.1.118 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 35 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (121-240) | RPP | 30.1.119 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 35 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (121-240) | RPP | 30.1.120 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 35 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.1 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.2 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.3 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.4 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.5 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.6 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.7 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.8 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.9 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.10 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.11 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.12 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.13 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.14 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.15 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.16 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.17 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.18 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.19 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.20 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.21 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.22 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.23 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.24 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.25 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.26 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.27 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.28 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.29 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.30 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.31 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.32 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.33 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.34 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.35 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.36 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.37 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.38 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.39 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.40 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.41 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.42 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.43 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.44 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.45 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.46 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.47 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.48 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.49 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.50 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.51 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.52 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.53 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.54 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.55 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.56 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.57 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.58 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.59 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.60 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.61 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.62 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.63 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.64 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.65 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.66 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.67 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.68 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.69 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.70 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.71 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.72 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.73 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.74 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.75 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.76 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.77 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.78 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.79 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.80 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.81 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.82 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.83 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.84 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.85 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.86 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.87 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.88 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.89 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.90 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.91 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.92 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.93 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.94 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.95 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.96 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.97 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.98 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.99 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.100 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.101 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.102 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.103 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.104 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.105 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.106 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.107 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.108 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.109 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.110 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.111 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.112 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.113 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.114 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.115 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.116 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.117 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.118 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.119 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (241-360) | RPP | 31.1.120 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 36 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.1 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.2 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.3 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.4 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.5 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.6 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.7 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.8 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.9 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.10 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.11 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.12 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.13 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.14 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.15 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.16 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.17 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.18 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.19 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.20 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.21 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.22 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.23 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.24 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.25 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.26 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.27 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.28 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.29 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.30 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.31 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.32 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.33 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.34 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.35 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.36 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.37 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.38 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.39 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.40 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.41 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.42 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.43 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.44 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.45 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.46 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.47 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.48 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.49 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.50 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.51 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.52 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.53 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.54 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.55 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.56 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.57 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.58 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.59 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.60 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.61 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.62 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.63 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.64 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.65 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.66 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.67 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.68 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.69 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.70 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.71 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.72 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.73 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.74 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.75 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.76 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.77 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.78 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.79 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.80 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.81 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.82 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.83 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.84 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.85 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.86 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.87 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.88 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.89 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.90 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.91 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.92 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.93 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.94 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.95 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.96 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.97 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.98 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.99 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.100 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.101 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.102 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.103 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.104 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.105 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.106 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.107 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.108 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.109 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.110 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.111 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.112 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.113 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.114 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.115 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.116 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.117 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.118 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.119 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
RPP's (361-480) | RPP | 32.1.120 | RPP's | RPP | [5 empty] | FALSE |  |  | 0% |  | 2.5 | 2.5 | 2.5 |  |  |  | 37 | 150 | 45225 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 1 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
[13 empty] | 0% |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Completed | Not Completed | Not Completed | 0 |  |  | 0 | Not Started | 0 | 0 |  |  |  | Not Started ¦ ¦
Formulas:
Date_Bin_Week = IF([DATE COMPLETED]="","Not Completed",IF([DATE COMPLETED]>=TODAY()-7,"This Week",IF([DATE COMPLETED]>=TODAY()-14,"Last Week",IF([DATE COMPLETED]>=TODAY()-30,"Last 30 Days","Older"))))
Date_Bin_Month = IF([DATE COMPLETED]="","Not Completed",IF(MONTH([DATE COMPLETED])=MONTH(TODAY()),"This Month",IF(MONTH([DATE COMPLETED])=MONTH(TODAY())-1,"Last Month",IF([DATE COMPLETED]>=DATE(YEAR(TODAY()),1,1),"This Year","Prior Year"))))
Date_Bin_Quarter = IF([DATE COMPLETED]="","Not Completed",IF(ROUNDUP(MONTH([DATE COMPLETED])/3,0)=ROUNDUP(MONTH(TODAY())/3,0),"This Quarter",IF(ROUNDUP(MONTH([DATE COMPLETED])/3,0)=ROUNDUP(MONTH(TODAY())/3,0)-1,"Last Quarter",IF(YEAR([DATE COMPLETED])=YEAR(TODAY()),"Earlier This Year","Prior Year"))))
Days_Since_Completed = IF([DATE COMPLETED]="","",TODAY()-[DATE COMPLETED])
DATE COMPLETED = [1]All_Tasks_Billing!L724
Week_Ending = [1]All_Tasks_Billing!AA724
Billable_Week = IF([Week_Ending]="","",[Week_Ending])